## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Balarampur PWSS under Kharagpur-II Block in Paschim Medinipur District | SM/09706 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Balarampur PWSS under Kharagpur-II Block in Paschim Medinipur District. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000492/2021-2022 | 2185/MD | 17/12/2021 | 16/01/2022 | S.T. ENTERPRISE | 61.78 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Balarampur PWSS under Kharagpur-II Block in Paschim Medinipur District | SM/09706 | Retrofitting | Extension of laying of distribution uPVC Pipe line Left-out portion and all allied works at i) Balarampur village (North side), ii) Balarampur village (South side) and Madhpur, iii) Some part of Krishnapur & Ramchandrapur and iv) Some part of Gobindanagar & Kanchantala under JJM of Balarampur & its adjoining mouzas W/S Scheme under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000477/2022-2023 | 2272/MD | 09/11/2022 | 09/12/2022 | S.T. ENTERPRISE | 21.85 | 0 | 0 | 100
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Balarampur PWSS under Kharagpur-II Block in Paschim Medinipur District | SM/09706 | Retrofitting | Retrofitting to accommodate FHTC (350 Nos.) including supplying, laying, fitting, fixing of 15mm dia. NB PVC (Sche-80/20mm dia.) HDPE (PE-100, PN-16) pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM of Balarampur W/S Scheme within Kharagpur-II Dev. block under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the district of Paschim Medinipur. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE3 Kharagpur Sub-division | ORD/000474/2022-2023 | 2269/MD | 09/11/2022 | 30/11/2022 | SUBRATA DAS | 13.21 | 0 | 0 | 100
Total | [13 empty] | 96.84 | 0 | 0