## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Nona Madhabchak PWSS under Sabang Block in Paschim Medinipur District | SM/09708 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Nona Madhabchak PWSS Block-Sabang in the District of Paschim Medinipur. | AE Kharagpur Sub-division |  | ORD/000411/2021-2022 | 2016/MD | 03/12/2021 | 01/02/2022 | DULAL CHANDRA DAS | 101.79 | 91.66 | 90.05 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Nona Madhabchak PWSS under Sabang Block in Paschim Medinipur District | SM/09708 | Retrofitting | Construction of Sluice Valve/Air Valve/wash out valve Chamber Over the distribution pipe line at within Nonamadhachak & its adjoining mouzas water Supply Scheme at Sabang Block under Kharagpur Sub-Division within Midnapore Division, P.H.E. Dte.(Part -I). | AE Kharagpur Sub-division |  | ORD/000059/2022-2023 | 487/AE/KSD | 01/08/2022 | 31/08/2022 | BADAL CHANDRA MAIKAP | 4.82 | 4.82 | 100 | 0
Total | [13 empty] | 106.61 | 96.48 | 90.5