## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Khagragerya PWSS under Sbang Block in Paschim Medinipur District | SM/09709 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Khagragerya PWSS, Block - Sabang in the District of Paschim Medinipur. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang Blk),JE RWS Kharagpur Sub-Division( Sabang) | ORD/000454/2021-2022 | 2093/MD | 10/12/2021 | 08/02/2022 | ASHOK BANERJEE | 108.34 | 43.38 | 40.04 | 50
Total | [13 empty] | 108.34 | 43.38 | 40.04