## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of ground water based Dhaneswarpur PWSS to accommodate FHTC under JJM under Dantan-II block in Paschim Medinipur District under medinipur Division,PHE DTE. | SM/09722 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Dhaneswarpur, Block - Dantan-II) to be Retrofitting under Midnapore Division P.H.E. Dte. |  |  | VCH/001716/2021-2022 | BP-2021-22-456 | 11/03/2022 | 11/03/2022 | SIRCON ENGINEERING SERVICES | 2.54 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of ground water based Dhaneswarpur PWSS to accommodate FHTC under JJM under Dantan-II block in Paschim Medinipur District under medinipur Division,PHE DTE. | SM/09722 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Dhaneswarpur, Block - Dantan-II) to be Retrofitting under Midnapore Division P.H.E. Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II) | ORD/000859/2020-2021 | 296/MD | 19/02/2021 | 01/03/2021 | SIRCON ENGINEERING SERVICES | 3.15 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of ground water based Dhaneswarpur PWSS to accommodate FHTC under JJM under Dantan-II block in Paschim Medinipur District under medinipur Division,PHE DTE. | SM/09722 | Retrofitting | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Dhaneswarpur PWSS to accommodate FHTC under JJM under Dantan-II block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II) | ORD/000476/2021-2022 | 2170/MD | 17/12/2021 | 21/01/2022 | UTTAM KUMAR DAS | 89.26 | 0 | 0 | 0
Total | [13 empty] | 94.94 | 0 | 0