## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of ground water based Baita PWSS to accommodate FHTC under JJM under Mohanpur block in Paschim Medinipur District under medinipur Division,PHE DTE. | SM/09724 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Baita, Block - Mohanpur) to be Retrofitting under Midnapore Division P.H.E. Dte. |  |  | VCH/001420/2021-2022 | BP-2021-22-416 | 24/02/2022 | 24/02/2022 | SIRCON ENGINEERING SERVICES | 2.47 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of ground water based Baita PWSS to accommodate FHTC under JJM under Mohanpur block in Paschim Medinipur District under medinipur Division,PHE DTE. | SM/09724 | Retrofitting | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Baita PWSS to accommodate FHTC under JJM under Mohanpur block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000413/2021-2022 | 2018/MD | 03/12/2021 | 01/02/2022 | M/S. A.R. ENTERPRISE. | 100.97 | 0 | 0 | 80
Total | [13 empty] | 103.44 | 0 | 0