## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of ground water based Sonakania PWSS to accommodate FHTC under JJM under Dantan-I block in Paschim Medinipur District under medinipur Division,PHE DTE. | SM/09725 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Sonakania, Block - Dantan-I) to be Retrofitting under Midnapore Division P.H.E. Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I) | ORD/000558/2020-2021 | 52/MD | 08/01/2021 | 18/01/2021 | SIRCON ENGINEERING SERVICES | 2.3 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of ground water based Sonakania PWSS to accommodate FHTC under JJM under Dantan-I block in Paschim Medinipur District under medinipur Division,PHE DTE. | SM/09725 | Retrofitting | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Sonakania PWSS to accommodate FHTC under JJM under Dantan-I block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I) | ORD/000404/2021-2022 | 2003/MD | 01/12/2021 | 16/12/2021 | M/S. EL-CON | 36.71 | 31.9 | 86.9 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of ground water based Sonakania PWSS to accommodate FHTC under JJM under Dantan-I block in Paschim Medinipur District under medinipur Division,PHE DTE. | SM/09725 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Sonakania, Block - Dantan-I) to be Retrofitting under Midnapore Division P.H.E. Dte. |  |  | VCH/001368/2021-2022 | BP-2021-22-417 | 24/02/2022 | 24/02/2022 | SIRCON ENGINEERING SERVICES | 1.69 | 0 | 0 | 0
Total | [13 empty] | 40.7 | 31.9 | 78.39