## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of ground water based piped water supply scheme for Jot Ghanashyam to accommodate FHTC. | SM/09726 | Retrofitting | Supply of C.I.D.F Sluice Valve & C.I. Jeffy coupler for distribution and Rising main pipe line for Retrofitting of JOTGHANASHYAM water Supply Scheme under Ghatal Sub-Division of Midnapore Division, P.H.E.Dte. | AE Ghatal Sub-division |  | ORD/000177/2022-2023 | 402/AE/GSD | 11/07/2022 | 18/07/2022 | GOBINDA MAITY | 4.5 | 4.5 | 100 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of ground water based piped water supply scheme for Jot Ghanashyam to accommodate FHTC. | SM/09726 | Retrofitting | Continuation Work Order for the work of Design with allied works in connection with the FHTC of existing PWSS Jot Ghanashyam (Block-Daspur-II) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE Ghatal Sub-division |  | ORD/001041/2021-2022 | 1653/MD | 23/09/2021 | 03/10/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.38 | 0.38 | 100 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of ground water based piped water supply scheme for Jot Ghanashyam to accommodate FHTC. | SM/09726 | Retrofitting | Preparation of D.P.R. in connection with the Functional Household Tap Connection of existing PWSS (Chandrakona Road Railway Station, Amlagora, Jot Ghanashyam & Sonakhali in various blocks) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. |  |  | VCH/001813/2021-2022 | BP-2021-22-470 | 11/03/2022 | 11/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.19 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Retrofitting of ground water based piped water supply scheme for Jot Ghanashyam to accommodate FHTC. | SM/09726 | Retrofitting | Laying of 25sq.mm armoured cable and electromechanical equipment at pump house no II of Jotghanashyam water supply scheme under Panschim Medinipur District under Midnapore Mechanical Division, P.H.E. Dte. |  |  | ORD/002151/2022-2023 | 196/MMSD-I | 28/02/2023 | 07/03/2023 | DIPALI CONSTRUCTION | 4.42 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of ground water based piped water supply scheme for Jot Ghanashyam to accommodate FHTC. | SM/09726 | Retrofitting | Retrofitting of Jot Ghanashyam Piped Water Supply Scheme to accommodate FHTC under Jal Swapna including Sinking of 1 nos. Tube Well and other allied Works in Daspur-II Block of Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000410/2021-2022 | 2015/MD | 03/12/2021 | 03/03/2022 | GOBINDA MAITY | 297.42 | 270.92 | 91.09 | 100
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting of ground water based piped water supply scheme for Jot Ghanashyam to accommodate FHTC. | SM/09726 | Retrofitting | Continuation Work Order for the work of "Retrofitting of Jot Ghanashyam Piped Water Supply Scheme to accommodate FHTC under Jal Swapna including Sinking of 1 nos. Tube Well and other allied Works in Daspur-II Block of Paschim Medinipur District under Midnapore Division, PHE Dte." | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000171/2022-2023 | 1242/MD | 20/06/2022 | 10/11/2025 | GOBINDA MAITY | 90.19 | 87.21 | 96.7 | 100
Total | [13 empty] | 398.11 | 363.01 | 91.18