## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur | SM/09795 | New | Preparation of D.P.R. (Consultancy work) in connection with Proposed Mini Pipe W/S Scheme for Uttar Eral mouza of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000419/2021-2022 | 1332/MD | 17/08/2021 | 27/08/2021 | GOBINDA MAITY | 2.17 | 2.17 | 99.89 | 0
2 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur | SM/09795 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Uttar Eral water supply scheme, Tube Well no. 1 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte.. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001205/2021-2022 | 73/W/MMD | 17/01/2022 | 22/01/2022 | SUJOY RANJAN BHOWMICK | 4.48 | 0 | 0 | 100
3 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur | SM/09795 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Uttar Eral water supply scheme, Tube Well no. 2 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte.. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001206/2021-2022 | 74/W/MMD | 17/01/2022 | 22/01/2022 | SUJOY RANJAN BHOWMICK | 4.48 | 0 | 0 | 100
4 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur | SM/09795 | New | Sinking of different dis T/W under mentioned Scheme of Sabang Block. |  |  | VCH/001829/2021-2022 | BP-2021-22-505 | 22/03/2022 | 22/03/2022 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 7.98 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur | SM/09795 | New | Electric quotation Chandkuri CCC? at L ttar Eral W/S Scheme i¿ui-721144 |  |  | VCH/000381/2022-2023 |  | 02/08/2022 | 02/08/2022 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.13 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur | SM/09795 | New | Electric quotation Chandkuri CCC at Uttar Eral W/S Scheme Pin:- 721144 |  |  | VCH/000382/2022-2023 |  | 03/08/2022 | 03/08/2022 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.13 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur | SM/09795 | New | Jhargram Mechanical Electrical Bill. |  |  | VCH/000947/2022-2023 | 2022-23-210 | 18/08/2022 | 18/08/2022 | EXECUTIVE ENGINEER, JHARGRAM MECHANICAL DIVISION, PHE DTE. | 0.25 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur | SM/09795 | New | For payment of liabilities. |  |  | VCH/001702/2021-2022 | BP-2021-22-445 | 08/03/2022 | 08/03/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 2.28 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur | SM/09795 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well-I at Uttar Eral, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001199/2021-2022 | 158/W/MMD | 31/01/2022 | 31/05/2022 | TAPAN KUMAR SARKAR | 6.47 | 6 | 92.77 | 0
10 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur | SM/09795 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well-II at Uttar Eral, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001200/2021-2022 | 159/W/MMD | 31/01/2022 | 31/05/2022 | RAJIB COMPANY | 6.46 | 5.99 | 92.8 | 0
11 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur | SM/09795 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Uttar Eral (Zone-I), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000892/2021-2022 | 469/MD | 09/03/2022 | 06/08/2022 | SUJATA CONSTRUCTION | 46.64 | 42.56 | 91.26 | 0
12 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur | SM/09795 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Uttar Eral (Zone-II), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000893/2021-2022 | 470/MD | 09/03/2022 | 06/08/2022 | SUJATA CONSTRUCTION | 37.67 | 29.11 | 77.28 | 0
13 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur | SM/09795 | New | Material Requisition To Resource Division |  |  | RTOR000013/2021-2022 | 2128/MD | 14/12/2021 | 14/12/2021 | Resource Division | 2.28 | 0 | 0 | 0
14 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Uttar Eral mouzas, Block - Sabang, District - Paschim Medinipur | SM/09795 | New | Restoration of damaged distribution system and other allied works in different locations of Single Village W/S Schemes (SVS) within Sabang Block under Midnapore Division P.H.E. Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang Blk) | ORD/000477/2024-2025 | 480/MD | 13/02/2025 | 14/04/2025 | A-PLUS | 22 | 0 | 0 | 100
Total | [13 empty] | 143.4 | 85.84 | 59.86