## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. | SM/09923 | Augmentation | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Amlagora (Block-Garhbeta-I) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE Sadar Sub-division |  | ORD/001032/2021-2022 | 1624/MD | 21/09/2021 | 01/10/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.01 | 3.01 | 100 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. | SM/09923 | Augmentation | Continuation Work Order for the work of Design with allied works in connection with the FHTC of existing PWSS Amlagora (Block-Garhbeta-I) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE Sadar Sub-division |  | ORD/001033/2021-2022 | 1625/MD | 21/09/2021 | 01/10/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.66 | 0.66 | 100 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. | SM/09923 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur under JJM Program under MMD PHE Dte. |  |  | ORD/001290/2022-2023 | 2293/W/MMD | 29/12/2022 | 27/06/2023 | DEBJYOTI BASU | 23 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. | SM/09923 | Augmentation | Laying distribution pipeline, Soil test and Construction of RCC Over Head Reservoir of capacity 200 CuM and staging height 20.00 mtr. with allied work including supply of all labour & materials for Augmentation of Amlagora W/S Scheme to accommodate FHTC with Garhbeta-I Dev. Block under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. Dist.- Paschim Medinipur. | AE Sadar Sub-division | JE1 Sadar Sub-division,JE2 Sadar Sub-division | ORD/000376/2022-2023 | 1959/MD | 20/09/2022 | 19/03/2023 | BANERJEE CONSTRUCTION | 606.57 | 363.7 | 59.96 | 33
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. | SM/09923 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2022-2023 | 2322/MD | 17/11/2022 | 17/11/2022 | Resource Division | 32.25 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. | SM/09923 | Augmentation | Preparation of D.P.R. in connection with the Functional Household Tap Connection of existing PWSS (Chandrakona Road Railway Station, Amlagora, Jot Ghanashyam & Sonakhali in various blocks) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. |  |  | VCH/001812/2021-2022 | BP-2021-22-470 | 11/03/2022 | 11/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.19 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. | SM/09923 | Augmentation | Design with allied works in connection with the Functional Household Tap Connection of existing PWSS (Amlagora, Block - Garhbeta-I) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. |  |  | VCH/001391/2021-2022 | BP-2021-22-387 | 18/02/2022 | 18/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.05 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. | SM/09923 | Augmentation | Conducting of Route Survey in connection with the Functional Household Tap Connection of existing PWSS (Amlagora, Block - Garhbeta-I) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. |  |  | VCH/001393/2021-2022 | BP-2021-22-383 | 18/02/2022 | 18/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.11 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. | SM/09923 | Augmentation | Repair and Renovation of Switch Room cum Chlorine Room No. 2 of Amlagora Water Supply Scheme within Midnapore Sadar Sub Division under Midnapore Division, PHE Dte. (SL No-02) | AE Sadar Sub-division |  | ORD/001032/2022-2023 | 983/AE/MSSD | 17/03/2023 | 01/04/2023 | MR GOUTAM GHOSH, | 0.97 | 0.92 | 95.68 | 10
10 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. | SM/09923 | Augmentation | Repair and Renovation of Switch Room cum Chlorine Room No. 1 of Amlagora Water Supply Scheme within Midnapore Sadar Sub Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division |  | ORD/001030/2022-2023 | 982/AE/MSSD | 17/03/2023 | 01/04/2023 | MR GOUTAM GHOSH, | 0.97 | 0.92 | 95.68 | 10
11 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. | SM/09923 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000115/2022-2023 | 244/MD | 18/01/2023 | 18/01/2023 | Resource Division | 100.02 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. | SM/09923 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2022-2023 | 137/MD | 11/01/2023 | 11/01/2023 | Resource Division | 32.25 | 0 | 0 | 0
13 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur. | SM/09923 | Augmentation | Construction of Boundary wall at 1st Tube well site for Augmentation of Amlagora PWSS, Block - Garhbeta-I, District - Paschim Medinipur under Midnapore Division, PHE Dte. (Total length 120 mtr., Column size 250X250mm, 3.00M, C/C ht.- 2.300 mtr. from G.L.) | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000104/2024-2025 | 2850/MD | 09/09/2024 | 08/11/2024 | AJITESH ACHARJEE | 11.39 | 0 | 0 | 0
Total | [13 empty] | 816.42 | 369.22 | 45.22