## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. | SM/09933 | Augmentation | Sinking of 125mm X 80mm dia. & 150 Mtr.Depth, Deep Tubewell by Water Jet System at Garhbeta Water Testing Lab Premises in the district of Paschim Medinipore under Midnapore Division PHE Dte.(SL No-01) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000194/2021-2022 | 438/AE/MSSD | 10/08/2021 | 25/08/2021 | S.T. ENTERPRISE | 2.87 | 1.87 | 65.08 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. | SM/09933 | Augmentation | Continuation Work Order for the work of Conducting of Route survey & Design with allied works in connection with the FHTC of existing PWSS Garhbeta (Block-Garhbeta-I) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/001040/2021-2022 | 1652/MD | 23/09/2021 | 03/10/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.69 | 2.69 | 100 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. | SM/09933 | Augmentation | Laying distribution pipe line, Providing FHTC, Soil test & Construction of R.C.C. Over Head Reservoir of capacity 500 Cum (Intze type with solid raft) and staging height 20.00 mtr. with allied work including Construction of 150 Cum capacity CWR for Augmentation of Garhbeta W/S Scheme in Garhbeta-I Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE1 Sadar Sub-division,JE2 Sadar Sub-division | ORD/000044/2022-2023 | 837/MD | 02/05/2022 | 29/10/2022 | BANERJEE CONSTRUCTION | 580.16 | 353.72 | 60.97 | 72
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. | SM/09933 | Augmentation | Hiring of 1 (one) no, Motor Cab(standard) commercial with catalytic converter attachment with Bharat Stage as per prevalent applicable standard compliant new/not older then 30 (thirty) months from the date of 1st registration on daily hire basis for 12 (twelve) months only having contract carriage permit for plying within west Bengal from Regional Transport Authority for the use of the Assistant Engineer, Midnapore Sadar Sub- Division PHE Dte. (It would be used only the 'JAL SWAPNA" Schematic Programme, inaugurated by Honorable C.M ) for the period of 06 (Six) months. | AE Sadar Sub-division |  | ORD/000259/2022-2023 | 470/AE/MSSD | 10/08/2022 | 10/02/2023 | SANJIT SINHA | 0.85 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. | SM/09933 | Augmentation | Repairing of damaged (due to flood) Rising main from river bank Tube Well to CWR of Garhbeta & its adjoining Mouzas W/S Scheme within Garhbeta Block under Midnapore Division PHE Dte. (SL No-02) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000258/2022-2023 | 467/AE/MSSD | 08/08/2022 | 22/09/2022 | CHANDAN YADAV | 0.81 | 0.55 | 67.54 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. | SM/09933 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000036/2021-2022 | 150/MD | 28/01/2022 | 28/01/2022 | Resource Division | 25.21 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. | SM/09933 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Garhbeta, Block - Garhbeta-I) to be Augmentation / Rejuvenation under Midnapore Division P.H.E. Dte. |  |  | VCH/001384/2021-2022 | BP-2021-22-398 | 08/02/2022 | 08/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.67 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. | SM/09933 | Augmentation | Hire and labour charges for staging and scaffolding, bamboo barricading and removal of rubbish for dismantling of existing OHR (Capacity 2,27,000 Ltr.) at Head work Site of Garhbeta Water Supply Scheme within Garhbeta-I Block under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. |  |  | VCH/001611/2021-2022 | BP-2021-22-421 | 02/03/2022 | 02/03/2022 | BISWAJIT BAG | 4.7 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. | SM/09933 | Augmentation | Purchasing of materials for the Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I. District - Paschim Medinipur. |  |  | VCH/000446/2022-2023 |  | 10/08/2022 | 10/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 25.21 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. | SM/09933 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. |  |  | ORD/000018/2023-2024 | 1134/W/MMD | 12/04/2023 | 09/10/2023 | ORIENTAL ENGINEERING CO. | 89.14 | 35.3 | 39.6 | 20
11 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. | SM/09933 | Augmentation | Sinking of 150 X 100 mm dia. X 150 Mtr. Depth Rig bored Tube well at Mouza Pochadohora, J.L No.618, G.P - Shyamnagar within Garhbeta -I Block under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000132/2023-2024 | 2587/MD | 21/07/2023 | 05/08/2023 | RUPKUMAR KARMAKAR | 5.91 | 4.39 | 74.3 | 100
12 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. | SM/09933 | Augmentation | Sinking of 150 X 100 mm dia. X 150 Mtr. Depth Rig bored Tube well at Kadra Nimnapalli, Pratiharpara, Mouza Kadra , J.L. No. 867, G.P - Kadra Uttarbil within Garhbeta-I Block under Midnapore Division PHE Dte. | AE Sadar Sub-division |  | ORD/000130/2023-2024 | 2585/MD | 21/07/2023 | 05/08/2023 | M/S. ZAMAN ENTERPRISE | 5.91 | 4.69 | 79.39 | 100
13 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. | SM/09933 | Augmentation | Sinking of 150 X 100 mm dia. X 150 Mtr. Depth Rig bored Tube well at Saradapara Manasatala, Mouza - Mohanpur, J.L. No. 838, G.P. - Kadra Uttarbil within Garhbeta-I Block under Midnapore Division PHE Dte. | AE Sadar Sub-division |  | ORD/000131/2023-2024 | 2586/MD | 21/07/2023 | 05/08/2023 | MANNA COMPUTER | 5.91 | 4.47 | 75.63 | 100
14 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. | SM/09933 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000147/2022-2023 | 518/MD | 20/02/2023 | 20/02/2023 | Resource Division | 90.05 | 0 | 0 | 0
15 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. | SM/09933 | Augmentation | Garbeta to Hoomgarh Road from chainage 0.00 Km- Restoration of damages due to laying of proposed underground pipeline by PHE in the district of Paschim Medinipur under Midnapore Division, P.W.D during the year 2022-23 |  |  | BILL/00146/2023-2024 | BP-2023-24-82 | 11/05/2023 | 11/05/2023 | EXECUTIVE ENGINEER, P.W.D | 5 | 0 | 0 | 0
16 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. | SM/09933 | Augmentation | Laying additional distribution pipeline for Augmentation of Garhbeta PWSS, Block - Garhbeta-I, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000557/2024-2025 | 811/MD | 25/03/2025 | 24/05/2025 | KISHORE GHOSH | 51.54 | 0 | 0 | 10
Total | [13 empty] | 900.63 | 407.68 | 45.27