## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. | SM/09979 | Augmentation | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Keshpur (Block-Keshpur) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE Sadar Sub-division |  | ORD/001036/2021-2022 | 1644/MD | 22/09/2021 | 02/10/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.04 | 3.04 | 100 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. | SM/09979 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2022-2023 | 2473/MD | 06/12/2022 | 06/12/2022 | Resource Division | 41.87 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. | SM/09979 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000015/2022-2023 | 2322/MD | 17/11/2022 | 17/11/2022 | Resource Division | 23.96 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. | SM/09979 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Keshpur, Block - Keshpur) to be Augmentation / Rejuvenation under Midnapore Division P.H.E. Dte. |  |  | VCH/001421/2021-2022 | BP-2021-22-397 | 22/02/2022 | 22/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.65 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. | SM/09979 | Augmentation | Sinking of 4 (Four) nos. 250 x 150 mm dia. X 220 mtr. depth deep tube well by direct rotary method for Augmentation of Keshpur W/S Scheme with in Keshpur Block under Midnapore Division, P.H.E. Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000571/2022-2023 | 121/MD | 10/01/2023 | 09/02/2023 | M/S. A.R. ENTERPRISE. | 41.34 | 26.91 | 65.1 | 70
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. | SM/09979 | Augmentation | PWD road challan |  |  | BILL/00704/2022-2023 | BP-2022-23-704 | 23/02/2023 | 23/02/2023 | EXECUTIVE ENGINEER, P.W.D | 90 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. | SM/09979 | Augmentation | Restoration of damage shoulder & flank etc to the different roads under Midnapore Highway Division (Damage caused during laying pipe line by public Health Engineering Department. |  |  | BILL/00368/2022-2023 |  | 19/02/2023 | 19/02/2023 | EXECUTIVE ENGINEER, P.W.D | 138 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. | SM/09979 | Augmentation | Electric quotation bill for Tw No-III of Keshpur water supply scheme.( Consumer ID-204052921.) |  |  | BILL/01866/2023-2024 | BP-2023-24-232 | 07/09/2023 | 07/09/2023 | WBSEDCL | 3.31 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. | SM/09979 | Augmentation | Electric quotation bill for Tw No- IV of Keshpur water supply scheme.(Conumer ID-204057049) |  |  | BILL/01867/2023-2024 | BP-2023-24-230 | 07/09/2023 | 07/09/2023 | WBSEDCL | 2.76 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. | SM/09979 | Augmentation | Electric quotation bill for Tw no-V of Keshpur water supply scheme.(Consumer ID-204051457) |  |  | BILL/01868/2023-2024 | BP-2023-24-231 | 07/09/2023 | 07/09/2023 | WBSEDCL | 2.67 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. | SM/09979 | Augmentation | Laying distribution pipe line, Soil test & Construction of R.C.C. Over Head Reservoir of capacity 550 Cum and staging height 20.00 mtr. with allied work for Augmentation of Keshpur and its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur),JE2 Sadar Sub-division | ORD/000229/2022-2023 | 1722/MD | 22/08/2022 | 15/08/2025 | M/S. A.R. ENTERPRISE. | 605.9 | 465.3 | 76.79 | 80
12 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. | SM/09979 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001293/2022-2023 | 2296/W/MMD | 29/12/2022 | 27/06/2023 | P.K.ENGINEERING | 22.88 | 18.2 | 79.55 | 20
13 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. | SM/09979 | Augmentation | Additional distribution pipe line under JJM with allied works for Augmentation of Keshpur & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000403/2023-2024 | 5105/MD | 31/10/2023 | 30/12/2023 | M/S. A.R. ENTERPRISE | 52.81 | 45.28 | 85.75 | 80
14 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. | SM/09979 | Augmentation | Continuation work order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001826/2023-2024 | 1685/MMSD-I | 19/12/2023 | 17/02/2024 | M/S BIKASH DE | 0.29 | 0 | 0 | 100
15 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. | SM/09979 | Augmentation | Fuel for Inspection Vehicle of covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission Program. [w.e.f. 01-01-2024 to 29-02-2024] | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002853/2023-2024 | 1698/MMSD-I | 19/12/2023 | 17/02/2024 | M/S BIKASH DE | 0.83 | 0 | 0 | 100
16 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. | SM/09979 | Augmentation | Additional quotation for effective new service connection at KESHPUR(Near Auditorium) in modified route. ( Augmentation of Keshpur PWSS) |  |  | BILL/03225/2023-2024 | BP-2023-24-480 | 27/12/2023 | 27/12/2023 | WBSEDCL | 2.96 | 0 | 0 | 0
17 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. | SM/09979 | Augmentation | Electric Quotation Bill. |  |  | BILL/00175/2023-2024 |  | 15/05/2023 | 15/05/2023 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 1.84 | 0 | 0 | 0
18 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. | SM/09979 | Augmentation | Sinking of 4 (Four) nos. 250 x 150 mm dia. X 220 mtr. depth deep tube well by direct rotary method for Augmentation of Keshpur W/S Scheme with in Keshpur Block under Midnapore Division, P.H.E. Dte. |  |  | BILL/02162/2023-2024 | BP-2023-24-514 | 20/12/2023 | 20/12/2023 | M/S. A.R. ENTERPRISE | 1.84 | 0 | 0 | 0
19 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. | SM/09979 | Augmentation | ELECRTIC QUOTATION BILL FOR TW NO-IV OF KESHPUR PWSS. (Ref Consumer ID-204189500) |  |  | BILL/03444/2023-2024 |  | 15/01/2024 | 15/01/2024 | WBSEDCL | 2.76 | 0 | 0 | 0
20 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. | SM/09979 | Augmentation | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002834/2023-2024 | 339/MMSD-I | 05/03/2024 | 05/01/2025 | M/S BIKASH DE | 6.3 | 0.14 | 2.17 | 50
21 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. | SM/09979 | Augmentation | Continuation work order for Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. (Vehicle No. WB 33 C 6546) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002164/2024-2025 | 1826/MMSD-I | 30/12/2024 | 29/06/2025 | M/S BIKASH DE | 3.69 | 0 | 0 | 0
22 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. | SM/09979 | Augmentation | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different ongoing piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.- w.e.f.-01-07-2025 to 28-02-2026 (Vehicle No. WB33C 6546) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000513/2025-2026 | 842/MMSD-I | 11/06/2025 | 09/02/2026 | M/S BIKASH DE | 3.66 | 0 | 0 | 0
Total | [13 empty] | 1057.35 | 558.86 | 52.86