## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. | SM/09980 | Augmentation | Day to day operation & maintenance of distribution system & Rising main (CI/DI/HDPE/UPVC) with all related structure i.e. OHR etc. of Sonakhali W/S Scheme under Midnapore Division P.H.E. Dte. (Period from 01/11/2021 to 31/12/2021) | AE Ghatal Sub-division |  | ORD/000575/2021-2022 | 743/A/AE/GSD | 26/10/2021 | 26/12/2021 | SUBHASIS DOLAI | 0.88 | 0 | 0 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. | SM/09980 | Augmentation | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Sonakhali (Block-Daspur-I) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE Ghatal Sub-division |  | ORD/001034/2021-2022 | 1642/MD | 22/09/2021 | 02/10/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.78 | 1.78 | 100 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. | SM/09980 | Augmentation | Continuation Work Order for the work of Design with allied works in connection with the FHTC of existing PWSS Sonakhali (Block-Daspur-I) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE Ghatal Sub-division |  | ORD/001035/2021-2022 | 1643/MD | 22/09/2021 | 02/10/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.41 | 0.41 | 100 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. | SM/09980 | Augmentation | Laying distribution pipe line, Pump House, FHTC & Construction of R.C.C. Over Head Reservoir of capacity 600 Cum (including Pile) and staging height 20.00 mtr. with allied work for Augmentation of Sonakhali W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000217/2022-2023 | 1688/MD | 16/08/2022 | 28/03/2026 | GOBINDA MAITY | 757.01 | 563.63 | 74.45 | 60
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. | SM/09980 | Augmentation | Conducting of Route Survey in connection with the Functional Household Tap Connection of existing PWSS (Sonakhali, Block - Daspur-II) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. |  |  | VCH/001395/2021-2022 | BP-2021-22-385 | 18/02/2022 | 18/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.4 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. | SM/09980 | Augmentation | Design with allied works in connection with the Functional Household Tap Connection of existing PWSS (Sonakhali, Block ¿ Daspur-II) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. |  |  | VCH/001414/2021-2022 | BP-2021-22-386 | 23/02/2022 | 23/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.87 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. | SM/09980 | Augmentation | Preparation of D.P.R. in connection with the Functional Household Tap Connection of existing PWSS (Chandrakona Road Railway Station, Amlagora, Jot Ghanashyam & Sonakhali in various blocks) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. |  |  | VCH/001814/2021-2022 | BP-2021-22-470 | 11/03/2022 | 11/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.19 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. | SM/09980 | Augmentation | Preliminarily Ground Protection works (i,e, Construction R.C.C. Retaining wall, Land development) And Rising main in connection with Construction of Boundary wall, OHR, Switch Room etc. at Head Works site of Augmentation of Sonakhali W/S Scheme under Midnapore Division P.H.E. Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000627/2022-2023 | 452/MD | 13/02/2023 | 15/03/2023 | GOBINDA MAITY | 25.92 | 6.37 | 24.55 | 25
9 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. | SM/09980 | Augmentation | Sinking of 3 (Three) nos. 250 x 150 mm dia. X 220 mtr. depth deep tube well by direct rotary method for Augmentation of Sonakhali W/S Scheme with in Daspur-II Block under Midnapore Division, P.H.E. Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000570/2022-2023 | 120/MD | 10/01/2023 | 31/01/2023 | PRANTIK DRILLING AGENCY | 29.59 | 27.37 | 92.47 | 100
10 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. | SM/09980 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. (Part-II) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001952/2022-2023 | 865/W/MMD | 27/03/2023 | 31/07/2025 | S.S.GHORAI | 13.68 | 12.94 | 94.54 | 95
11 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. | SM/09980 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001592/2022-2023 | 452/W/MMD | 20/03/2023 | 31/07/2025 | SAIKAT SINHA | 27.36 | 22.99 | 84.01 | 71
12 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. | SM/09980 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000167/2022-2023 | 901/MD | 31/03/2023 | 31/03/2023 | Resource Division | 75.94 | 0 | 0 | 0
13 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. | SM/09980 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2022-2023 | 133/MD | 11/01/2023 | 11/01/2023 | Resource Division | 28.24 | 0 | 0 | 0
14 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. | SM/09980 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000148/2022-2023 | 531/MD | 21/02/2023 | 21/02/2023 | Resource Division | 75.94 | 0 | 0 | 0
15 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. | SM/09980 | Augmentation | Electric Quotation ID No. 204047232 |  |  | BILL/01614/2023-2024 | BP-2023-24-132 | 20/07/2023 | 20/07/2023 | WBSEDCL | 3.07 | 0 | 0 | 0
16 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. | SM/09980 | Augmentation | Electric Quotation for SONAKHALI Water Supply Scheme T/W-II (Ref. ID-204046818 ) |  |  | BILL/01615/2023-2024 | BP-2023-24-133 | 20/07/2023 | 20/07/2023 | WBSEDCL | 5.24 | 0 | 0 | 0
17 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. | SM/09980 | Augmentation | Construction of 3.60 Mtr. X 3.00 Mtr. Switch Room cum Chlorine Room with out W.C. & Bath for 2nd. Tube Well site of Augmentation of Sonakhali water supply scheme within Ghatal Sub-Division under Midnapore Division, PHE Dte. (Considering G.L. 1950 mm below Road Level) {TYPE - B} | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000129/2024-2025 | 1495/AE/GSD | 24/09/2024 | 12/03/2025 | SK REAJUL HOSSAIN | 3.64 | 0 | 0 | 100
Total | [13 empty] | 1055.18 | 635.48 | 60.22