## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Kutulpur Piped Water Supply Scheme. | SM/09988 | New | Sinking of (Two) nos. 250 X 150 mm dia. X 120 mtr. Depth deep tube well by direct rotary method for Kutulpur & adjoining mouzas W/S Scheme within Ghatal Block under Midnapore Division, P.H.E. Dte. | AE Ghatal Sub-division | JE2 Ghatal Sub-division | ORD/000109/2023-2024 | 2491/MD | 17/07/2023 | 31/07/2023 | MIDNAPUR PIPE CONCERN | 13.37 | 13.33 | 99.71 | 100
2 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Kutulpur Piped Water Supply Scheme. | SM/09988 | New | Material Requisition To Resource Division |  |  | RTOR000124/2022-2023 | 337/MD | 31/01/2023 | 31/01/2023 | Resource Division | 18.14 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Kutulpur Piped Water Supply Scheme. | SM/09988 | New | KOTULPUR WATER SUPPLY SCHEME, T W NO 1, JJM WORKS, SCHEME CODE SM/09988, APPLICATION NO 2004606465, REFERENCE ID 204221239, BIRSINGHA CCC, WBSEDCL |  |  | BILL/04221/2023-2024 | BP-2023-24-768 | 04/03/2024 | 04/03/2024 | WBSEDCL | 2.67 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Kutulpur Piped Water Supply Scheme. | SM/09988 | New | KOTULPUR WATER SUPPLY SCHEME, T W NO 2, JJM WORKS, SCHEME CODE SM/09988, APPLICATION NO 2004606516, REFERENCE ID 204221238, BIRSINGHA CCC, WBSEDCL |  |  | BILL/04223/2023-2024 | BP-2023-24-767 | 04/03/2024 | 04/03/2024 | WBSEDCL | 4.14 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Kutulpur Piped Water Supply Scheme. | SM/09988 | New | Laying distribution pipe line, soil test & construction of R.C.C. Over Head Reservoir of capacity 250 Cum ( Pile Foundation) and staging height 20.00 mtr. & FHTC under JJM with allied work for Kotulpur and its adjoining mouzas W/S scheme in Ghatal Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE2 Ghatal Sub-division | ORD/000374/2022-2023 | 1957/MD | 20/09/2022 | 14/03/2026 | DIPAK KUMAR DOLAI | 306.49 | 99.42 | 32.44 | 72
6 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Kutulpur Piped Water Supply Scheme. | SM/09988 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Kutulpur Water supply scheme,Ghatal block, District - Paschim Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000391/2024-2025 | 2007/W/MMD | 30/08/2024 | 26/02/2025 | M/S S M ELECTRICAL | 27 | 4.5 | 16.65 | 80
7 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Kutulpur Piped Water Supply Scheme. | SM/09988 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002832/2023-2024 | 340/MMSD-I | 05/03/2024 | 05/01/2025 | SUBHASIS ROY | 6.3 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Kutulpur Piped Water Supply Scheme. | SM/09988 | New | Laying of rising main & inter connection for Kutulpur & its adjoining mouzas PWSS within block - Ghatal, Dist.- Paschim Medinipur under Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000511/2024-2025 | 621/MD | 05/03/2025 | 19/04/2025 | SUBHASIS DOLAI | 5.67 | 0 | 0 | 0
Total | [13 empty] | 383.79 | 117.25 | 30.55