## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Soil Investigation, Construction of R.C.C. Elevated Reservoir of Capacity 400 cum and staging height 20.00 mtr. (Pile Foundation) with allied works, Laying Distribution System of HDPE (PE-100) and Providing of FHTC for Antla and its adjoining mouzas Water Supply Scheme within Mohanpur Block in the district of Paschim Medinipur under Midnapore Division, P.H.E. Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),JE3 Kharagpur Sub-division | ORD/000515/2021-2022 | 2255/MD | 28/12/2021 | 31/05/2025 | MASUM ALI KHAN | 332.28 | 256.85 | 77.3 | 99
2 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Supply & delivery of different dia. C.I.D.F. Sluice Valves for laying of Distribution main pipeline for Antla Piped water Supply Scheme within Mohanpur Block under Kharagpur Sub-division of Midnapore Division, PHE Dte. In Paschim Medinipur District (Part -II) | AE/RWS Midnapore Sub Division |  | ORD/000085/2022-2023 | 312/AE/KSD | 10/06/2022 | 25/06/2022 | GOBINDA MAITY | 3.51 | 3.51 | 100 | 0
3 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Laying of distribution HDPE Pipe line of Left-Out portion and all allied works at Antla and its adjoining mouzas W/S Scheme under Kharagpur Sub-Division of Midnapore Division of Midnapore Division, PHE Dte. (Phase-I) | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000231/2022-2023 | 536/AE/KSD | 23/08/2022 | 22/09/2022 | PALASH KUMAR DAS | 4.81 | 4.81 | 100 | 0
4 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Construction of 3.60 Mtr. X 3.00 Mtr. Switch Room cum Chlorine Room with out W.C. & Bath for Second Tube Well Site under Antla W/S Scheme within Midnapore Division, PHE Dte. (Considering G.L. 300 mm below road level) (Type -A) | AE/RWS Midnapore Sub Division |  | ORD/000239/2022-2023 | 544/AE/KSD | 23/08/2022 | 22/09/2022 | PRITI ENTERPRISE | 2.79 | 2.7 | 96.64 | 0
5 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Laying of distribution HDPE pipe line of Left-out portion and all allied works at Antla and its adjoining mouzas W/S Scheme under Kharagpur Sub-Division of Midnapore Division, PHE Dte. (Phase-II) | AE/RWS Midnapore Sub Division |  | ORD/000232/2022-2023 | 537/AE/KSD | 23/08/2022 | 22/09/2022 | PALASH KUMAR DAS | 4.78 | 4.78 | 100 | 0
6 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Laying of distribution HDPE pipe line of Left-out portion and all allied works at Antla and its adjoining mouzas W/S Scheme under Kharagpur Sub-Division of Midnapore Division, PHE Dte. (Phase-III) Location Mathuribar ICDS & Kharpara | AE/RWS Midnapore Sub Division |  | ORD/000233/2022-2023 | 538/AE/KSD | 23/08/2022 | 22/09/2022 | PALASH KUMAR DAS | 4.85 | 4.85 | 100 | 0
7 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Sinking of 2 (Two) Nos. 300 X 200 mm dia. X 220 Mtr. Depth deep tube well by Direct Rotary Method for Head Work site & 2nd Tube well site of Antla W/S Scheme with in Mohanpur block under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000692/2021-2022 | 289/MD | 15/02/2022 | 02/03/2022 | KISHORE GHOSH | 21.82 | 16.76 | 76.83 | 100
8 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Material Requisition To Resource Division |  |  | RTOR000038/2021-2022 | 148/MD | 28/01/2022 | 28/01/2022 | Resource Division | 10.97 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Material Requisition To Resource Division |  |  | RTOR000004/2022-2023 | `2430/MD | 29/11/2022 | 29/11/2022 | Resource Division | 82.33 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Continuation Work Order for the work of Laying Balance Distribution System to accommodate FHTC of Proposed Pipe Water Supply Scheme for Antla & its adjoining Mouzas, Block: - Mohanpur, District: - Paschim Midnapore. (Total Length = 11,200.00 Mtr.) | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000611/2022-2023 | 383/MD | 03/02/2023 | 04/04/2023 | MASUM ALI KHAN | 53.34 | 52.15 | 97.77 | 0
11 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Construction of 5.40 Mtr. X 3.60 Mtr. Switch Room cum Chlorine Room with W.C. & Bath for Head Works Site under Antla W/S Scheme within Midnapore Division, PHE Dte. (Considering G.L. 300 mm below road level) (Type - A) | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000619/2022-2023 | 444/MD | 13/02/2023 | 14/04/2023 | MASUM ALI KHAN | 5.21 | 4.49 | 86.09 | 0
12 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Mechanical | Antla Piped Water Supply Scheme. | SM/09991 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Antla Piped Water Supply Scheme. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000001/2023-2024 | 1103/W/MMD | 05/04/2023 | 02/10/2023 | WEST BENGAL ENGINEERING CO. | 23.74 | 22.68 | 95.54 | 87
13 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 932/MD | 04/04/2023 | 04/04/2023 | Resource Division | 57.12 | 0 | 0 | 0
14 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Electric Quotation for Antla PWSS Tube well-I in connection Mohanpur CCC. |  |  | BILL/00073/2023-2024 | BP-2023-24-31 | 01/05/2023 | 01/05/2023 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 2.72 | 0 | 0 | 0
15 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Mechanical | Antla Piped Water Supply Scheme. | SM/09991 | New | Eletrict quotation bill for Atla water supply scheme at PH-II(Consumar Id-860286126) |  |  | BILL/03070/2023-2024 |  | 28/11/2023 | 28/11/2023 | WBSEDCL | 2.88 | 0 | 0 | 0
16 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Electric quotation bill for Atla Water supply Scheme at PH-II (Consumar Id-860286126) [MB-No- 3179/MMD] |  |  | BILL/00990/2023-2024 | BP-2023-24-509 | 15/12/2023 | 15/12/2023 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 2.88 | 0 | 0 | 0
17 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Electric Quotation for Antla PWSS Tube well-II in connection Mohanpur CCC. |  |  | BILL/00074/2023-2024 | BP-2023-24-30 | 01/05/2023 | 01/05/2023 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 2.99 | 0 | 0 | 0
18 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Laying of Rising Main including interconnection and all other allied works for Antla and its adjoining mouzas Water Supply Scheme within Mohanpur Block under Kharagpur Sub Division of Midnapore Division, P.H.E.Dte. | AE/RWS Midnapore Sub Division,Assistant Engineer (HQ) | JE3 Kharagpur Sub-division | ORD/001105/2023-2024 | 0107/RWS/MID | 29/02/2024 | 14/04/2024 | PALASH KUMAR DAS | 14.32 | 0 | 0 | 100
Total | [13 empty] | 633.35 | 373.58 | 58.98