## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Sinking of 2 (Two) Nos. 300 X 200 mm dia. X 220 Mtr. Depth deep tube well by Direct Rotary Method for Head Work site & 2nd Tube well site of Antla W/S Scheme with in Mohanpur block under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000692/2021-2022 | 289/MD | 15/02/2022 | 02/03/2022 | KISHORE GHOSH | 21.82 | 0 | 0 | 100
2 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Supply & delivery of different dia. C.I.D.F. Sluice Valves for laying of Distribution main pipeline for Antla Piped water Supply Scheme within Mohanpur Block under Kharagpur Sub-division of Midnapore Division, PHE Dte. In Paschim Medinipur District (Part -II) | AE/RWS Midnapore Sub Division |  | ORD/000085/2022-2023 | 312/AE/KSD | 10/06/2022 | 25/06/2022 | GOBINDA MAITY | 3.51 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Laying of distribution HDPE pipe line of Left-out portion and all allied works at Antla and its adjoining mouzas W/S Scheme under Kharagpur Sub-Division of Midnapore Division, PHE Dte. (Phase-II) | AE/RWS Midnapore Sub Division |  | ORD/000232/2022-2023 | 537/AE/KSD | 23/08/2022 | 22/09/2022 | PALASH KUMAR DAS | 4.78 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Laying of distribution HDPE Pipe line of Left-Out portion and all allied works at Antla and its adjoining mouzas W/S Scheme under Kharagpur Sub-Division of Midnapore Division of Midnapore Division, PHE Dte. (Phase-I) | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000231/2022-2023 | 536/AE/KSD | 23/08/2022 | 22/09/2022 | PALASH KUMAR DAS | 4.81 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Laying of distribution HDPE pipe line of Left-out portion and all allied works at Antla and its adjoining mouzas W/S Scheme under Kharagpur Sub-Division of Midnapore Division, PHE Dte. (Phase-III) Location Mathuribar ICDS & Kharpara | AE/RWS Midnapore Sub Division |  | ORD/000233/2022-2023 | 538/AE/KSD | 23/08/2022 | 22/09/2022 | PALASH KUMAR DAS | 4.85 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Construction of 3.60 Mtr. X 3.00 Mtr. Switch Room cum Chlorine Room with out W.C. & Bath for Second Tube Well Site under Antla W/S Scheme within Midnapore Division, PHE Dte. (Considering G.L. 300 mm below road level) (Type -A) | AE/RWS Midnapore Sub Division |  | ORD/000239/2022-2023 | 544/AE/KSD | 23/08/2022 | 22/09/2022 | PRITI ENTERPRISE | 2.79 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Continuation Work Order for the work of Laying Balance Distribution System to accommodate FHTC of Proposed Pipe Water Supply Scheme for Antla & its adjoining Mouzas, Block: - Mohanpur, District: - Paschim Midnapore. (Total Length = 11,200.00 Mtr.) | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000611/2022-2023 | 383/MD | 03/02/2023 | 04/04/2023 | MASUM ALI KHAN | 53.34 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Construction of 5.40 Mtr. X 3.60 Mtr. Switch Room cum Chlorine Room with W.C. & Bath for Head Works Site under Antla W/S Scheme within Midnapore Division, PHE Dte. (Considering G.L. 300 mm below road level) (Type - A) | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000619/2022-2023 | 444/MD | 13/02/2023 | 14/04/2023 | MASUM ALI KHAN | 5.21 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Material Requisition To Resource Division |  |  | RTOR000038/2021-2022 | 148/MD | 28/01/2022 | 28/01/2022 | Resource Division | 10.97 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Material Requisition To Resource Division |  |  | RTOR000004/2022-2023 | `2430/MD | 29/11/2022 | 29/11/2022 | Resource Division | 82.33 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 932/MD | 04/04/2023 | 04/04/2023 | Resource Division | 57.12 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Electric Quotation for Antla PWSS Tube well-II in connection Mohanpur CCC. |  |  | BILL/00074/2023-2024 | BP-2023-24-30 | 01/05/2023 | 01/05/2023 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 2.99 | 0 | 0 | 0
13 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Electric Quotation for Antla PWSS Tube well-I in connection Mohanpur CCC. |  |  | BILL/00073/2023-2024 | BP-2023-24-31 | 01/05/2023 | 01/05/2023 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 2.72 | 0 | 0 | 0
14 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Mechanical | Antla Piped Water Supply Scheme. | SM/09991 | New | Eletrict quotation bill for Atla water supply scheme at PH-II(Consumar Id-860286126) |  |  | BILL/03070/2023-2024 |  | 28/11/2023 | 28/11/2023 | WBSEDCL | 2.88 | 0 | 0 | 0
15 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Mechanical | Antla Piped Water Supply Scheme. | SM/09991 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Antla Piped Water Supply Scheme. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000001/2023-2024 | 1103/W/MMD | 05/04/2023 | 02/10/2023 | WEST BENGAL ENGINEERING CO. | 23.74 | 0 | 0 | 87
16 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Electric quotation bill for Atla Water supply Scheme at PH-II (Consumar Id-860286126) [MB-No- 3179/MMD] |  |  | BILL/00990/2023-2024 | BP-2023-24-509 | 15/12/2023 | 15/12/2023 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 2.88 | 0 | 0 | 0
17 | PASCHIM MEDINIPUR | Mohanpur | Midnapore Division | Antla Piped Water Supply Scheme. | SM/09991 | New | Soil Investigation, Construction of R.C.C. Elevated Reservoir of Capacity 400 cum and staging height 20.00 mtr. (Pile Foundation) with allied works, Laying Distribution System of HDPE (PE-100) and Providing of FHTC for Antla and its adjoining mouzas Water Supply Scheme within Mohanpur Block in the district of Paschim Medinipur under Midnapore Division, P.H.E. Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),JE3 Kharagpur Sub-division | ORD/000515/2021-2022 | 2255/MD | 28/12/2021 | 31/05/2025 | MASUM ALI KHAN | 332.28 | 0 | 0 | 99
Total | [13 empty] | 619.03 | 0 | 0