## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. | SM/09999 | Augmentation | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Pingla (Block-Pingla) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE Kharagpur Sub-division |  | ORD/001038/2021-2022 | 1646/MD | 22/09/2021 | 02/10/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.15 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. | SM/09999 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Pingla, Block - Pingla) to be Augmentation / Rejuvenation under Midnapore Division P.H.E. Dte. |  |  | VCH/001389/2021-2022 | BP-2021-22-396 | 22/02/2022 | 22/02/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.62 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. | SM/09999 | Augmentation | Continuation Work Order for the work of Laying Balance Distribution System to accommodate FHTC of Proposed Augmentation Pipe Water Supply Scheme for Pingla & its adjoining Mouzas, Block: - Pingla, District: - Paschim Midnapore. Total Length = 12,600.00 Mtr. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | ORD/000539/2022-2023 | 2467/MD | 05/12/2022 | 03/02/2023 | GOBINDA MAITY | 68.72 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. | SM/09999 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. |  |  | ORD/001308/2022-2023 | 2310/W/MMD | 29/12/2022 | 27/06/2023 | SHOVAN KUMAR DAS | 25.52 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. | SM/09999 | Augmentation | Sinking of 2 (Two) nos. 250 x 150 mm dia. X 220 mtr. depth deep tube well by direct rotary method for Augmentation of Pingla W/S Scheme with in Pingla Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | ORD/000579/2022-2023 | 229/MD | 17/01/2023 | 31/01/2023 | GOBINDA MAITY | 20.68 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. | SM/09999 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000122/2022-2023 | 335/MD | 31/01/2023 | 31/01/2023 | Resource Division | 20.85 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. | SM/09999 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2022-2023 | 139/MD | 11/01/2023 | 11/01/2023 | Resource Division | 21.67 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. | SM/09999 | Augmentation | Electric quotation for Pingla PWSS Tube Well-III WS Scheme (Ref. ID 203917728) |  |  | BILL/00398/2022-2023 | BP-2022-23-146 | 27/03/2023 | 27/03/2023 | WBSEDCL | 0.49 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. | SM/09999 | Augmentation | Electric Quotation for Add tw no- IV of Pingla w/s scheme.(Consumer ID-203970943) |  |  | BILL/00082/2023-2024 | BP-2023-24-23 | 28/04/2023 | 28/04/2023 | WBSEDCL | 2.83 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. | SM/09999 | Augmentation | Professional fee bill for the Registration of Land under W.B registration rules 1962, at D.S.R-I, Midnapore for below mention details. |  |  | BILL/00239/2022-2023 |  | 31/01/2023 | 31/01/2023 | BADAL CHANDRA BERA | 0.63 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. | SM/09999 | Augmentation | Laying distribution pipe line, Soil test and Construction of R.C.C. Over Head Reservoir of capacity 400 CuM and staging height 20.00 mtr. with allied work including supply of all labour & materials for Augmentation of Pingla & its adjoining mouzas Water Supply Scheme within Pingla Dev. Block under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. Dist. Paschim Medinipur. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000124/2022-2023 | 1311/MD | 30/06/2022 | 26/11/2025 | GOBINDA MAITY | 668 | 0 | 0 | 100
12 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. | SM/09999 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur.under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000148/2023-2024 | 1375/W/MMD | 30/05/2023 | 09/04/2025 | SHOVAN KUMAR DAS | 25.24 | 0 | 0 | 20
13 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. | SM/09999 | Augmentation | Balance work to accommodate FHTC of Augmentation Pipe Water Supply Scheme for Pingla & its adjoining mouzas, Block - Pingla, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000377/2024-2025 | 52/MD | 07/01/2025 | 23/03/2025 | GOBINDA MAITY | 62.68 | 0 | 0 | 100
Total | [13 empty] | 924.06 | 0 | 0