## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Masharpur mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10002 | New | Quotation Bill of Mosharpur water supply scheme under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000160/2022-2023 | 2003978639 | 28/06/2022 | 28/06/2023 | WBSEDCL | 0.11 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Masharpur mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10002 | New | Quotation Bill of Mosharpur water supply scheme under MMD PHE Dte. |  |  | VCH/001774/2022-2023 | BP-2022-23-45 | 23/08/2022 | 23/08/2022 | WBSEDCL | 0.11 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Masharpur mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10002 | New | Purchasing of materials for the ground Based Mini Piped Water Supply Scheme for Masharpur mouza under SAGY, Block - Ghatal. GP - Dewanchak-11, PS - Ghatal, Dist.- Paschim Medinipur. |  |  | VCH/000442/2022-2023 |  | 10/08/2022 | 10/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.64 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Masharpur mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10002 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-II under Masharpur water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist. Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001243/2022-2023 | 2174/W/MMD | 12/12/2022 | 11/04/2023 | SUBHASIS ROY | 5.92 | 5.38 | 90.82 | 91
5 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Masharpur mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10002 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-I under Masharpur water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist Paschim Medinipur | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000224/2022-2023 | 1653/W/MMD | 12/08/2022 | 10/12/2022 | BHABANI PRASAD MANNA | 5.64 | 5.64 | 100 | 100
6 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Masharpur mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10002 | New | Material Requisition To Resource Division |  |  | RTOR000034/2021-2022 | 2273/MD | 31/12/2021 | 31/12/2021 | Resource Division | 1.64 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Masharpur mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10002 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme under SAGY for Mouza- Masharpur (Zone-I), Block - Ghatal, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Ghatal) | ORD/000715/2021-2022 | 319/MD | 17/02/2022 | 17/07/2022 | PULLOCK KUMAR GHOSH | 39.42 | 30.66 | 77.78 | 100
8 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Masharpur mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10002 | New | Continuation Work Order for Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme under SAGY for Mouza- Masharpur (Zone-I), Block ¿ Ghatal, District ¿ Paschim Medinipur under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Ghatal) | ORD/001077/2022-2023 | 433/MD | 10/02/2023 | 25/02/2023 | PULLOCK KUMAR GHOSH | 0.84 | 0.84 | 100 | 100
9 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Masharpur mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10002 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme under SAGY for Mouza- Masharpur (Zone-II), Block - Ghatal, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000021/2022-2023 | 618/MD | 04/04/2022 | 01/01/2024 | DEVJYOTI BERA | 36.33 | 29.1 | 80.1 | 90
Total | [13 empty] | 91.65 | 71.62 | 78.15