## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10003 | New | Preparation of D.P.R (Consultancy work) in connection with the Proposed Mini Pipe Water Supply Scheme for Mouza- Dewanchak under Dewanchak¿II Gram Panchayat of SAGY (Sanshad Adarshya Gram Yagona) within Ghatal Block under Midnapore Division, P.H.E. Dte. | AE Ghatal Sub-division |  | ORD/000416/2021-2022 | 1329/MD | 17/08/2021 | 27/08/2021 | SIRCON ENGINEERING SERVICES | 2.34 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10003 | New | Quotation Bill of PH-II, Dewanchak water supply scheme under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000159/2022-2023 | 2003978672 | 28/06/2022 | 28/06/2023 | WBSEDCL | 0.11 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10003 | New | Service Connection charges of WBSEDCL at Dewanchak, Chowka, Dewanchak P/H-I | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000168/2022-2023 | 2003978666 | 28/06/2022 | 28/06/2023 | WBSEDCL | 0.11 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10003 | New | Purchasing of materials for the ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY |  |  | VCH/000441/2022-2023 |  | 10/08/2022 | 10/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 4.04 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10003 | New | Quotation Bill of PH-I, Dewanchak water supply scheme under MMD PHE Dte. |  |  | VCH/001783/2022-2023 | BP-2022-23-23 | 08/08/2022 | 08/08/2022 | WBSEDCL | 0.11 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10003 | New | Electric quotation for Birsingha CCC, Zone-II, Dewanchak water supply scheme under MMD PHE Dte, Pin no.-14/10/2022 |  |  | VCH/002565/2022-2023 | 2004068300 | 17/10/2022 | 17/10/2022 | WBSEDCL | 0.11 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10003 | New | Purchasing of materials for the ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY. Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. |  |  | VCH/000444/2022-2023 |  | 10/08/2022 | 10/08/2022 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 4.04 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10003 | New | Submission of bill for cleaning head work site, supplying, fitting, fixing RCC demarcation pillers etc. of Mini pipe water supply schemes under SAGY. |  |  | VCH/000251/2022-2023 | BP-2022-23-01 | 18/04/2022 | 18/04/2022 | SUBHASIS DOLAI | 0.25 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10003 | New | Quotation Bill of PH-II, Dewanchak water supply scheme under MMD PHE Dte. |  |  | VCH/001773/2022-2023 | BP-2022-23-46 | 23/08/2022 | 23/08/2022 | WBSEDCL | 0.11 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10003 | New | electric quotation for Birsingha CCC, Zone-I Dewanchak water supply scheme undre MMD PHE Dte. Pin No.-721232 |  |  | VCH/002566/2022-2023 | 2004068257 | 17/10/2022 | 17/10/2022 | WBSEDCL | 0.11 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10003 | New | Submission of bill for cleaning head work site, supplying, fitting, fixing RCC demarcation pillers etc. of Mini pipe water supply schemes under SAGY. |  |  | VCH/000252/2022-2023 | BP-2022-23-02 | 18/04/2022 | 18/04/2022 | SUBHASIS DOLAI | 0.42 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10003 | New | Electric quotation for Birsingha CCC, Dewanchak water supply scheme Zone-II, Pin no-721232 |  |  | ORD/001072/2022-2023 | 2003788821../Quot/03 | 06/08/2022 | 06/08/2023 | WBSEDCL | 0.11 | 0 | 0 | 0
13 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10003 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-II under Dewanchak water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist. Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001242/2022-2023 | 2173/W/MMD | 12/12/2022 | 11/04/2023 | PADMA ENGINEERING CO. | 5.93 | 0 | 0 | 0
14 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10003 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-III under Dewanchak water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist Paschim Medinipur | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000220/2022-2023 | 1649/W/MMD | 12/08/2022 | 10/12/2022 | KAMAKSHYA ENTERPRISE | 5.6 | 0 | 0 | 98
15 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10003 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-IV under Dewanchak water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist Paschim Medinipur | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000221/2022-2023 | 1650/W/MMD | 12/08/2022 | 10/12/2022 | SHOVAN KUMAR DAS | 5.75 | 0 | 0 | 100
16 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10003 | New | Material Requisition To Resource Division |  |  | RTOR000035/2021-2022 | 2274/MD | 31/12/2021 | 31/12/2021 | Resource Division | 4.04 | 0 | 0 | 0
17 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10003 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme under SAGY for Mouza- Dewanchak (Zone-I), Block-Ghatal, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000697/2021-2022 | 293/MD | 15/02/2022 | 15/07/2022 | DIPAK KUMAR DOLAI | 42.69 | 0 | 0 | 100
18 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10003 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme under SAGY for Mouza- Dewanchak (Zone-IV), Block-Ghatal, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000698/2021-2022 | 294/MD | 15/02/2022 | 15/07/2022 | SAMIT PAL | 39.22 | 0 | 0 | 100
19 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10003 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme under SAGY for Mouza- Dewanchak (Zone-II), Block - Ghatal, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000920/2021-2022 | 539/MD | 22/03/2022 | 19/08/2022 | M/S. ZAMAN ENTERPRISE | 36.07 | 0 | 0 | 100
20 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10003 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme under SAGY for Mouza- Dewanchak (Zone-III), Block-Ghatal, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000907/2021-2022 | 525/MD | 21/03/2022 | 18/08/2022 | WATER LINK | 41.84 | 0 | 0 | 100
21 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY, Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | SM/10003 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-I under Dewanchak water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist. Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001241/2022-2023 | 2172/W/MMD | 12/12/2022 | 10/05/2025 | P.K.ENGINEERING | 5.91 | 0 | 0 | 100
Total | [13 empty] | 198.87 | 0 | 0