## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | Monoharpur Piped Water Supply Scheme. | SM/10017 | New | Laying distribution pipe line, Soil test & Construction of R.C.C. Over Head Reservoir of capacity 500 Cum and staging height 20.00 mtr. & FHTC under JJM with allied work for Monoharpur and its adjoining mouzas W/S Scheme in Datan-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I) | ORD/000472/2022-2023 | 2190/MD | 01/11/2022 | 14/10/2025 | JDJ ENTERPRISE (A UNIT OF JDJ TRADERS PRIVATE LIMITED) | 583.38 | 138.71 | 23.78 | 35
2 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | Monoharpur Piped Water Supply Scheme. | SM/10017 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KAKRAJIT AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001922/2022-2023 | 841/W/MMD | 24/03/2023 | 20/09/2023 | P.K.ENGINEERING | 54.76 | 25.68 | 46.9 | 30
3 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | Monoharpur Piped Water Supply Scheme. | SM/10017 | New | Laying Rising main pipe line, Construction of Pump House & Boundary wall under JJM with allied work for Monoharpur & its adjoining mouzas PWSS in Dantan-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I) | ORD/000203/2023-2024 | 2817/MD | 07/08/2023 | 06/10/2023 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 29.64 | 20.73 | 69.95 | 76
4 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | Monoharpur Piped Water Supply Scheme. | SM/10017 | New | Sinking of 2 (Two) nos. 300 X 200 mm dia. X 200 mtr. depth deep tube well by direct rotary method for Head work site & 2nd tube well site of Monoharpur PWSS with in Dantan - I block under Midnapore Division, P.H.E. Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I) | ORD/000622/2022-2023 | 447/MD | 13/02/2023 | 27/02/2023 | FIROJ KHAN | 23.18 | 22.73 | 98.05 | 0
5 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | Monoharpur Piped Water Supply Scheme. | SM/10017 | New | Material Requisition To Resource Division |  |  | RTOR000164/2022-2023 | 802/MD | 20/03/2023 | 20/03/2023 | Resource Division | 20.04 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | Monoharpur Piped Water Supply Scheme. | SM/10017 | New | Material Requisition To Resource Division |  |  | RTOR000060/2022-2023 | 49/MD | 06/01/2023 | 06/01/2023 | Resource Division | 25.82 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | Monoharpur Piped Water Supply Scheme. | SM/10017 | New | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 941/MD | 05/04/2023 | 05/04/2023 | Resource Division | 20.04 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | Monoharpur Piped Water Supply Scheme. | SM/10017 | New | New service connection at Monoharpur T.W.No-II |  |  | BILL/00118/2023-2024 |  | 08/05/2023 | 08/05/2023 | WBSEDCL | 2.5 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | Monoharpur Piped Water Supply Scheme. | SM/10017 | New | Electric Quotation Bill for the West Bengal State Electricty Distribution Company LTD. |  |  | BILL/00250/2023-2024 | BP-2023-24-142 | 23/06/2023 | 23/06/2023 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 3.27 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | Monoharpur Piped Water Supply Scheme. | SM/10017 | New | Quotation for new service connection at Monoharpur T.W.no-I |  |  | BILL/00117/2023-2024 |  | 08/05/2023 | 08/05/2023 | WBSEDCL | 0.78 | 0 | 0 | 0
Total | [13 empty] | 763.4 | 207.85 | 27.23