## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Panna Piped Water Supply Scheme. | SM/10065 | New | Sinking of 200 mm x 100 mm dia. X 156 Mtr. Depth Rig bored Tube wells at 2nd Tube well site with Laying of uPVC (Class-III) & DI pipeline with FHTC works, Construction of 3.60 Mtr. X 3.00 Mtr. Switch Room & Boundary wall, Laying of Rising main at 2nd T/W site for Panna W/S Scheme within Ghatal Block of Ghatal Sub-Division under Midnapore Division, PHE Dte. (PART- B) | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Ghatal) | ORD/000466/2022-2023 | 2186/MD | 01/11/2022 | 28/03/2025 | S.N ENTERPRISE | 67.2 | 44.84 | 66.72 | 5
2 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Panna Piped Water Supply Scheme. | SM/10065 | New | Soil investigation work in connection with Construction of RCC OHR, Construction & Commissioning of 150 CuM RCC OHR with FHTC works for Panna W/S Scheme within Ghatal Block of Ghatal Sub-Division under Midnapore Division, PHE Dte. (PART- C) | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Ghatal) | ORD/000542/2022-2023 | 2673/MD | 30/12/2022 | 28/05/2025 | CHAKRABORTTI ENTERPRISE | 86.3 | 15.72 | 18.21 | 12
3 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Panna Piped Water Supply Scheme. | SM/10065 | New | Sinking of 200 mm x 100 mm dia. X 156 Mtr. Depth Rig bored Tube wells at Head Works cum 1st Tube well site with Laying of uPVC (Class-III) & DI pipeline, Construction of 5.40 Mtr. X 3.60 Mtr. Switch Room & Boundary wall for Panna W/S Scheme within Ghatal Block of Ghatal Sub-Division under Midnapore Division, PHE Dte. (PART- A) | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Ghatal) | ORD/000208/2022-2023 | 1673/MD | 12/08/2022 | 31/12/2024 | M/S. D.K.H.CONSTRUCTION | 65.06 | 53.97 | 82.96 | 100
4 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Panna Piped Water Supply Scheme. | SM/10065 | New | Electric Quotation. {Enter in MB No:- 3068, Page No:- 165} |  |  | BILL/00061/2022-2023 | BP-2022-23-468 | 27/12/2022 | 27/12/2022 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.46 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Panna Piped Water Supply Scheme. | SM/10065 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Panna Piped Water Supply Scheme under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001891/2022-2023 | 789/W/MMD | 24/03/2023 | 02/10/2025 | A G ENTERPRISE | 22.77 | 9.34 | 41.02 | 80
6 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Panna Piped Water Supply Scheme. | SM/10065 | New | Installation of Dept. Submersible Pump motor set and with other supplied items and other allied works at Tubewell no 1 of Panna Water Supply Scheme Block Ghatal under MMD, PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001605/2023-2024 | 1546/MMSD-I | 12/12/2023 | 27/12/2023 | SHOVAN KUMAR DAS | 1.29 | 0 | 0 | 100
7 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Panna Piped Water Supply Scheme. | SM/10065 | New | Material Requisition To Resource Division |  |  | RTOR000029/2022-2023 | 135/MD | 11/01/2023 | 11/01/2023 | Resource Division | 4.73 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Panna Piped Water Supply Scheme. | SM/10065 | New | Material Requisition To Resource Division |  |  | RTOR000166/2022-2023 | 888/MD | 30/03/2023 | 30/03/2023 | Resource Division | 21.77 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Panna Piped Water Supply Scheme. | SM/10065 | New | Material Requisition To Resource Division |  |  | RTOR000007/2023-2024 | 1134/MD | 24/04/2023 | 24/04/2023 | Resource Division | 21.77 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Panna Piped Water Supply Scheme. | SM/10065 | New | QUOTATION MONEY FOR PANNA WATER SUPPLY SCHEME, T W NO 2, [ BLOCK GHATAL ] JJM WORKS, SCHEME CODE SM/110065, APPLICATION NO 2004843733, REFERENCE ID 204368914, GHATAL CCC, WBSEDCL |  |  | BILL/00499/2024-2025 | BP-2024-25-458 | 12/11/2024 | 12/11/2024 | WBSEDCL | 5.57 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Panna Piped Water Supply Scheme. | SM/10065 | New | ADDITIONAL QUOTATION MONEY FOR PANNA WATER SUPPLY SCHEME,T W - II , JJM WORKS, SCHEME CODE SM/ 10065, , APPLICATION NO 100000149552, REFERENCE ID 860348792, GHATAL CCC, WBSEDCL |  |  | BILL/03048/2025-2026 |  | 14/11/2025 | 14/11/2025 | WBSEDCL | 0.88 | 0 | 0 | 0
Total | [13 empty] | 297.79 | 123.87 | 41.6