## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Gobindanagar Piped Water Supply Scheme | SM/10066 | New | Sinking of 2 (Two) Nos. 200 X 100 mm dia. X 180 Mtr. depth Rig bored tube wells at Head Works cum 1st Tube well & 2nd tube well sites of Gobindanagar W/S Scheme within Daspur-I Block of Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000125/2022-2023 | 1312/MD | 30/06/2022 | 15/07/2022 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 12.8 | 11.78 | 92.06 | 100
2 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Gobindanagar Piped Water Supply Scheme | SM/10066 | New | Supply of C.I.D.F Sluice Valve & C.I. Jeffy coupler for distribution and Rising main pipe line for GOBINDANAGAR water Supply Scheme under Ghatal Sub-Division of Midnapore Division, P.H.E.Dte. | AE Ghatal Sub-division |  | ORD/000176/2022-2023 | 401/AE/GSD | 11/07/2022 | 18/07/2022 | SUBHASIS DOLAI | 3.22 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Gobindanagar Piped Water Supply Scheme | SM/10066 | New | Exigency basis laying casing pipe under Bitumineous pucca road crosssing near Goura Bridge,Sarala Ciname of Khakurda to Ghatal PWD Road of Gobindanagar W/S Scheme within Ghatal Sub-Division, PHE.Dte. | AE Ghatal Sub-division |  | ORD/000511/2022-2023 | 165/AE/GSD | 01/04/2022 | 03/04/2022 | SUBHASIS DOLAI | 3.64 | 3.41 | 93.7 | 0
4 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Gobindanagar Piped Water Supply Scheme | SM/10066 | New | Exigency basis laying casing pipe under Bitumineous pucca road crosssing Near Anapurna Nursing Home,Panchberia Bus Stop, Nirmal Paludhi house of Khakurda to Ghatal PWD Road of Gobindanagar W/S Scheme within Ghatal Sub-Division, PHE.Dte. | AE Ghatal Sub-division |  | ORD/000512/2022-2023 | 166/AE/GSD | 01/04/2022 | 03/04/2022 | SUBHASIS DOLAI | 3.64 | 3.4 | 93.59 | 0
5 | PASCHIM MEDINIPUR | Daspur-I | Central Drilling | Gobindanagar Piped Water Supply Scheme | SM/10066 | New | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (200 MM X 100 MM) WITH IN gHATAL BLOCK (PASCHIM MEDINIPUR) UNDER CENTRAL DRILLING DIVISION, PHE DTE. |  |  | ORD/000010/2021-2022 | 387/CDD | 23/08/2021 | 07/09/2021 | MENAKA ENTERPRISE | 8.73 | 6.19 | 70.98 | 0
6 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Gobindanagar Piped Water Supply Scheme | SM/10066 | New | Construction of RCC Pile for Over Head Reservoir (in place of Intze type with solid raft) of capacity 300 CuM and Staging height 20 mtr. as per approved drawing (No:- PC-I/OHR/07/2012) with allied works for Gobindanagar & its adjoining Mouzas W/S Scheme within Daspur-I block including supply of all labour & materials under Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000475/2022-2023 | 2270/MD | 09/11/2022 | 09/12/2022 | DIPAK KUMAR DOLAI | 36.58 | 10.31 | 28.2 | 100
7 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Gobindanagar Piped Water Supply Scheme | SM/10066 | New | Continuation Work Order for the work of Laying additional distribution pipe line for Gobindanagar Water Supply Scheme under Daspur-I block within Midnapore Division PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000595/2022-2023 | 219/MD | 16/01/2023 | 15/02/2023 | DIPAK KUMAR DOLAI | 13.3 | 13.3 | 100 | 100
8 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Gobindanagar Piped Water Supply Scheme | SM/10066 | New | Material Requisition To Resource Division |  |  | RTOR000130/2022-2023 | 378/MD | 03/02/2023 | 03/02/2023 | Resource Division | 25.32 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Gobindanagar Piped Water Supply Scheme | SM/10066 | New | Electric quotation for Gobindanagar PWSS Tube Well-II at under Daspur Customer Care Centre |  |  | BILL/00034/2022-2023 | BP-2022-23-83 | 27/12/2022 | 27/12/2022 | WBSEDCL | 0.46 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Gobindanagar Piped Water Supply Scheme | SM/10066 | New | Electric quotation for Gobindanagar PWSS Tube Well-III (Ref. ID-203924590) |  |  | BILL/00162/2022-2023 | BP-2022-23-130 | 14/03/2023 | 14/03/2023 | WBSEDCL | 0.47 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Gobindanagar Piped Water Supply Scheme | SM/10066 | New | Electric quotation for Gobindanagar PWSS T/W-I at under Daspur CCC |  |  | BILL/00032/2022-2023 | BP-2022-23-82 | 27/12/2022 | 27/12/2022 | WBSEDCL | 0.46 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Gobindanagar Piped Water Supply Scheme | SM/10066 | New | Flank restoration of Panskura Ghatal Road from 15.00 kmp to 17.00 kmp under Midnapore Highway Division in the District of Paschim Medinipur. |  |  | BILL/00127/2023-2024 | BP-2023-24-80 | 08/05/2023 | 08/05/2023 | EXECUTIVE ENGINEER, P.W.D | 20 | 0 | 0 | 0
13 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Gobindanagar Piped Water Supply Scheme | SM/10066 | New | Construction of RCC Pile for Over Head Reservoir (in place of Intze type with solid raft) of capacity 300 CuM and Staging height 20 mtr. as per approved drawing (No:- PC-I/OHR/07/2012) with allied works for Gobindanagar & its adjoining Mouzas W/S Scheme within Daspur-I block including supply of all labour & materials under Midnapore Division, PHE Dte. |  |  | BILL/00706/2022-2023 | BP-2022-23-665 | 04/03/2023 | 04/03/2023 | DIPAK KUMAR DOLAI | 24 | 0 | 0 | 0
14 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Gobindanagar Piped Water Supply Scheme | SM/10066 | New | Laying rising main, Pump houses (5.40 X 3.60 Mtr.) & (3.60 X 3.00 Mtr.), Boundary wall, Approach road for Gobindanagar Piped Water Supply Scheme within Daspur-I Block under Ghatal Sub-Division of Midnapore Division PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000381/2022-2023 | 1964/MD | 20/09/2022 | 19/11/2022 | DEBASISH DOGRA | 34.31 | 7.55 | 21.99 | 65
15 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Gobindanagar Piped Water Supply Scheme | SM/10066 | New | Continuation Work Order for the work of Laying additional pipeline for Gobindanagar W/S Scheme in Daspur-I block within Ghatal Sub-Division under Midnapore Division PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000010/2023-2024 | 962/MD | 06/04/2023 | 05/06/2023 | DIPAK KUMAR DOLAI | 52.61 | 51.91 | 98.66 | 95
16 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Gobindanagar Piped Water Supply Scheme | SM/10066 | New | Supply and installation of chlorination and fenching and civil works for protection of pumping machinaries at Tube Well no III of Gobindanagar Water Supply Scheme [ Block- Daspur-I] under MMD, PHE Dte., Dist.- Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002710/2023-2024 | 318/MMSD-I | 04/03/2024 | 14/03/2024 | S.S.GHORAI | 1.72 | 0 | 0 | 0
17 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Gobindanagar Piped Water Supply Scheme | SM/10066 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Gobindanagar(Add. Tube Well No.-III) Piped Water Supply Scheme under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001880/2022-2023 | 778/W/MMD | 24/03/2023 | 20/09/2023 | S.S.GHORAI | 8.17 | 6.35 | 77.75 | 100
18 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Gobindanagar Piped Water Supply Scheme | SM/10066 | New | Replacement and upgradation work of Voltage Stabilizer for Tube well No. 1 and 2 of Gobindanagar Water Supply Scheme Block Daspur I under MMD, PHE Dte., Dist. Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001303/2023-2024 | 1227/MMSD-I | 03/10/2023 | 02/11/2023 | BALAJI CONSTRUCTION | 5.17 | 5.17 | 100 | 100
19 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Gobindanagar Piped Water Supply Scheme | SM/10066 | New | Laying distribution pipe line, soil test, FHTC & construction of R.C.C. Over Head Reservoir of capacity 300 Cum and staging height 20.00 mtr. with allied work for Gobindanagar W/S Scheme in Daspur-I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000045/2022-2023 | 838/MD | 02/05/2022 | 27/03/2026 | DIPAK KUMAR DOLAI | 238.12 | 171.87 | 72.18 | 81
Total | [13 empty] | 492.69 | 291.23 | 59.11