## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. | SM/10091 | Augmentation | Sinking of 125 mm X 80 mm.dia. & 138 Mtr. Depth, Tubewell Including installation of pumping machinery and accessories etc at Chandrakona Road Headwork site in the district of Pashcim Medinipur under Midnapore Division, P.H.E. Dte. (SL No-05) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000069/2022-2023 | 223/AE/MSSD | 13/05/2022 | 02/06/2022 | CHANDAN YADAV | 3.03 | 2.23 | 73.63 | 90
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. | SM/10091 | Augmentation | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Chandrakona (Block-Garhbeta-III) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/001030/2021-2022 | 1622/MD | 21/09/2021 | 01/10/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.06 | 3.06 | 100 | 100
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. | SM/10091 | Augmentation | Continuation Work Order for the work of Design with allied works in connection with the FHTC of existing PWSS Chandrakona (Block-Garhbeta-III) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/001031/2021-2022 | 1623/MD | 21/09/2021 | 01/10/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.9 | 0.9 | 100 | 100
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. | SM/10091 | Augmentation | Conducting of Route Survey in connection with the Functional Household Tap Connection of existing PWSS (Chandrakona Road Railway Station, Block - Garhbeta-III) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. |  |  | VCH/001729/2021-2022 | BP-2021-22-468 | 16/03/2022 | 16/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.28 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. | SM/10091 | Augmentation | Hire and labour charges for staging and scaffolding, bamboo barricading and removal of rubbish for dismantling of existing OHR (Capacity 2,27,000 Ltr.) at Head work Site of Chandrakona Road Railway Station Water Supply Scheme (Zone-I) within Garhbeta-III Block under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. |  |  | VCH/001620/2021-2022 | BP-2021-22-424 | 02/03/2022 | 02/03/2022 | BISWAJIT BAG | 4.72 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. | SM/10091 | Augmentation | Design with allied works in connection with the Functional Household Tap Connection of existing PWSS (Chandrakona Road Railway Station, Block - Garhbeta-III) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. |  |  | VCH/001730/2021-2022 | BP-2021-22-469 | 16/03/2022 | 16/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.21 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. | SM/10091 | Augmentation | Preparation of D.P.R. in connection with the Functional Household Tap Connection of existing PWSS (Chandrakona Road Railway Station, Amlagora, Jot Ghanashyam & Sonakhali in various blocks) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. |  |  | VCH/001810/2021-2022 | BP-2021-22-470 | 11/03/2022 | 11/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.19 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. | SM/10091 | Augmentation | Hiring of 01 (one) no, Motor Cab(standard) commercial with catalytic converter attachment with Bharat Stage as per prevalent applicable standard compliant new/not older then 30 (thirty) months from the date of 1st registration on daily hire basis for 12 (twelve) months only having contract carriage permit for plying within west Bengal from Regional Transport Authority for the use of the Executive Engineer,Midnapore Division PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000357/2021-2022 | 474/AE/MSSD | 30/08/2021 | 30/08/2022 | SUKUMAR SANTRA | 1.7 | 0 | 0 | 100
9 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. | SM/10091 | Augmentation | Continuation Work Order for the work of Hiring of 01 (one) no. Motor Cab (standard) commercial with catalytic converter attachment with Bharat Stage as perprevalent applicable standard compliant new/not older then 30 (thirty) months from the date of 1st registration on daily hire basis for 6 (six) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Executive Engineer, Midnapore Division, PHE Dte. w.e.f. 01.09.2022 to 28.02.2023. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000409/2022-2023 | 503/AE/MSSD | 29/08/2022 | 05/02/2023 | SUKUMAR SANTRA | 0.9 | 1.43 | 158.97 | 100
10 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. | SM/10091 | Augmentation | Continuation Work order for Hiring of 1 (one) no, Motor Cab (standard) Commercial with Catalytic Converter attachment with Bharat Stage as per prevalent applicable standard compliant new /not older than 30 (thirty) months from the date of 1st registration on daily hire rate basis for 06 (Six) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, (HQ) under Midnapore Division PHE Dte. for the Period of 6 ( Six ) months. | AE Sadar Sub-division |  | ORD/000755/2022-2023 | 680/AE/MSSD | 30/11/2022 | 31/05/2023 | PULLOCK KUMAR GHOSH | 1.01 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. | SM/10091 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 1121/MD | 20/04/2023 | 20/04/2023 | Resource Division | 111.82 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. | SM/10091 | Augmentation | Car Bill |  |  | BILL/00314/2023-2024 | BP-2023-24-001 | 01/04/2023 | 01/04/2023 | SUKUMAR SANTRA | 0.8 | 0 | 0 | 0
13 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. | SM/10091 | Augmentation | Laying distribution pipeline, Providing FHTC, Soil test and Construction of RCC Over Head Reservoir of capacity 550 CuM (Intez type with solid raft) and staging height 20.00 mtr. with allied work including Sinking of Rig bored tube well for Augmentation of Chandrakona Road Rly. Station (Zone-I) Water Supply Scheme in Garhbeta-III block including supply of all labour & materials within Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000377/2022-2023 | 1960/MD | 20/09/2022 | 19/03/2023 | BANERJEE CONSTRUCTION | 588.73 | 256.78 | 43.62 | 25
14 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. | SM/10091 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. |  |  | ORD/001963/2022-2023 | 874/W/MMD | 27/03/2023 | 23/09/2023 | ORIENTAL ENGINEERING CO. | 23.76 | 11.13 | 46.86 | 95
15 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. | SM/10091 | Augmentation | Repair and Rennovation of Switch Room cum Chlorine Room ( No. 2 ) of Chandrakona Road Water Supply Scheme ( Zone-II ) within Midnapore Sadar Sub Division under Midnapore Division, PHE Dte. (SL No-03) | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-III) | ORD/001036/2022-2023 | 984/AE/MSSD | 17/03/2023 | 01/04/2023 | NAYAN CONSTRUCTION | 0.97 | 0.96 | 99 | 100
16 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. | SM/10091 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000069/2024-2025 | 3387/MD | 25/11/2024 | 25/11/2024 | Resource Division | 58.96 | 0 | 0 | 0
17 | PASCHIM MEDINIPUR |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. | SM/10091 | Augmentation | Quotation for Dedicated Transformer for C.K Road Z - I P.H - III water supply scheme. |  |  | BILL/00942/2024-2025 | 331/JMD | 29/08/2024 | 29/08/2024 | WBSEDCL | 4.42 | 0 | 0 | 0
18 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. | SM/10091 | Augmentation | Laying distribution pipe line, Providing FHTC and Sinking of Rig Bored Tube well for Augmentation of Chandrakona Road Rly. Station (Zone-II) W/S Scheme in Garhbeta-III Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000908/2021-2022 | 526/MD | 21/03/2022 | 11/12/2025 | GOBINDA MAITY | 459.24 | 281.4 | 61.28 | 75
19 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. | SM/10091 | Augmentation | Route survey & way leave permission along & across of National Highway in Augmentation of Chandrakona Road Railway Station (Zone-I) PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | AE Sadar Sub-division |  | ORD/000460/2024-2025 | 372/MD | 31/01/2025 | 21/02/2025 | DONA ASSOCIATES | 11.47 | 0 | 0 | 0
20 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. | SM/10091 | Augmentation | Laying Rising main from Common manifold to OHR for Augmentation of Chandrakona Road ( Zone-II ) W/S scheme within Garhbeta-III Block under Midnapur Division P.H.E. Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-III),JE2 Sadar Sub-division | ORD/000602/2022-2023 | 853/AE/MSSD | 03/02/2023 | 01/07/2025 | GOBINDA MAITY | 3.33 | 0 | 0 | 70
21 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. | SM/10091 | Augmentation | Laying of Rising Main for Augmentation of Chandrakona Road (Zone-II) & its adjoining mouzas PWSS Block: - Garbeta-III, District: - Paschim Midnapor under Midnapore Division, PHE Dte. (Length = 1,405 Mtr.) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000074/2024-2025 | 2783/MD | 03/09/2024 | 26/06/2025 | GOBINDA MAITY | 9.6 | 0 | 0 | 80
22 | PASCHIM MEDINIPUR |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. | SM/10091 | Augmentation | Quotation for dedicated transformar at C. K road Zone-I P.H-I water supply scheme |  |  | BILL/01647/2024-2025 | 472/JMD | 30/01/2025 | 30/01/2025 | WBSEDCL | 4.39 | 0 | 0 | 0
Total | [13 empty] | 1302.5 | 557.89 | 42.83