## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. | SM/10124 | Augmentation | Extension of laying of distribution UPVC pipe line in Gopalpur village Basti of Keshiary GP Within Keshiry W/S Scheme under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000671/2021-2022 | 114/AE/KSD | 09/03/2022 | 08/04/2022 | NIMAI LAL GURIA | 2.55 | 0 | 0 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. | SM/10124 | Augmentation | Continuation Work Order for the work of Design with allied works in connection with the FHTC of existing PWSS Keshiary (Block- Keshiary) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE Kharagpur Sub-division |  | ORD/001028/2021-2022 | 1620/MD | 21/09/2021 | 01/10/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.41 | 0 | 0 | 100
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. | SM/10124 | Augmentation | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Keshiary (Block- Keshiary) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE Kharagpur Sub-division |  | ORD/001029/2021-2022 | 1621/MD | 21/09/2021 | 01/10/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.87 | 0 | 0 | 100
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. | SM/10124 | Augmentation | Conducting of Route Survey in connection with the Functional Household Tap Connection of existing PWSS (Keshiary, Block - Keshiary) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. |  |  | VCH/001728/2021-2022 | BP-2021-22-467 | 16/03/2022 | 16/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.24 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. | SM/10124 | Augmentation | Design with allied works in connection with the Functional Household Tap Connection of existing PWSS (Keshiary, Block - Keshiary) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. |  |  | VCH/001727/2021-2022 | BP-2021-22-466 | 16/03/2022 | 16/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.76 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. | SM/10124 | Augmentation | Continuation Work order for the work Hiring of Bharat Stage- II/III / diesel motor cab (Luxury Taxi) / Maruti Omni (Standard Non-AC) having contract carriage permit from the regional transport authority for the Office of the Assistant Engineer, Kharagpur Sub- Division, P.H.E. Dte. [Period for 04.02.2022 to 20.03.2022] | AE Sadar Sub-division |  | ORD/000896/2021-2022 | 59/AE/KSD | 03/02/2022 | 20/03/2022 | SANJIT SINHA | 0.25 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. | SM/10124 | Augmentation | Sinking of 1(one) No. 125mm X 80mm dia. & 150 Mtr. Depth Deep Tube well including construction of Community Storage Tank (2000 Ltr. Capacity) and Installation of Submersible pumping machineries etc. for Creation of drinking water source at Chandana village, vide J.L.No. -47, Plot No.-1530(near house of Dhananjoy Mandi), GP- Khajra, Block- Keshiary under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in Paschim Medinipur District. | Assistant Engineer (HQ) |  | ORD/000058/2022-2023 | 486/AE/KSD | 01/08/2022 | 31/08/2022 | ASSOCIATED ENGINEERS & TRADERS | 4.41 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. | SM/10124 | Augmentation | Sinking of 4 (Four) nos. 250 x 150 mm dia. X 220 mtr. depth deep tube well by direct rotary method for Augmentation of Keshiary W/S Scheme with in Keshiary block under Midnapore Division, P.H.E. Dte. | Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary) | ORD/000620/2022-2023 | 445/MD | 13/02/2023 | 15/03/2023 | KISHORE GHOSH | 41.07 | 0 | 0 | 100
9 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. | SM/10124 | Augmentation | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations under (1) Augmentation of Keshiary & its adjoining mouzas W/S Scheme within Keshiary block & (2) Augmentation of Satkui & its adjoining mouzas W/S Scheme within Kharagpur-I block in Paschim Medinipur District through Jadavpur University. | AE Kharagpur Sub-division |  | ORD/000617/2022-2023 | 471/MD | 15/02/2023 | 01/03/2023 | JADAVPUR UNIVERSITY | 9.56 | 0 | 0 | 100
10 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. | SM/10124 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. (Part-III) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002028/2022-2023 | 936/W/MMD | 28/03/2023 | 24/09/2023 | EMCON | 11.49 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. | SM/10124 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2022-2023 | 138/MD | 11/01/2023 | 11/01/2023 | Resource Division | 29.36 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. | SM/10124 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000275/2023-2024 | 3988/MD | 06/10/2023 | 06/10/2023 | Resource Division | 29.18 | 0 | 0 | 0
13 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. | SM/10124 | Augmentation | Electric quotation bill for Ad Tw no-IV of Keshiary PWSS. (Ref Consumer ID-204117417) |  |  | BILL/02905/2023-2024 | BP-2023-24-329 | 03/11/2023 | 03/11/2023 | WBSEDCL | 3.2 | 0 | 0 | 0
14 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. | SM/10124 | Augmentation | Electric quotation bill for Ad Tw no-III of Keshaiary PWSS . Ref Consumer ID-204117416) |  |  | BILL/02904/2023-2024 | BP-2023-24-328 | 03/11/2023 | 03/11/2023 | WBSEDCL | 4.24 | 0 | 0 | 0
15 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. | SM/10124 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. (Part-II) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001953/2022-2023 | 866/W/MMD | 27/03/2023 | 23/09/2023 | S.S.GHORAI | 23.01 | 0 | 0 | 20
16 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. | SM/10124 | Augmentation | ADDITIONAL QUOTATION FOR SHIFTING OF LTOH AT CENTRAL BUS STAND PH NO-III OF KESHIARY PWSS, REFERENCE ID-860319179,APPLICATION ID-100000125209, APPLICATION TYPE- DEPOSIT WORKS OTHER THAN SERVICE CONNECTION, NAME OF CCC-KESHAIRY CCC, NAME OF BLOCK- KESHIARY. |  |  | BILL/03672/2024-2025 |  | 18/12/2024 | 18/12/2024 | WBSEDCL | 0.92 | 0 | 0 | 0
17 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. | SM/10124 | Augmentation | Laying distribution pipe line, Soil test and Construction of R.C.C. Over Head Reservoir of capacity 200 Cum and staging height 20.00 mtr. with allied work including supply of all labour & materials for Augmentation of Keshiary & its adjoining mouzas Water Supply Scheme to accomodate FHTC within Keshiary Block under Kharagpur Sub-Division of Midnapore Division, P.H.E.Dte. Dist. Paschim Medinipur. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000227/2022-2023 | 1734/MD | 23/08/2022 | 07/03/2026 | M/S. A.R. ENTERPRISE. | 601.47 | 0 | 0 | 80
18 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. | SM/10124 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001292/2022-2023 | 2295/W/MMD | 29/12/2022 | 30/05/2025 | BUSR ENGINEERING | 22.99 | 0 | 0 | 20
19 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. | SM/10124 | Augmentation | Laying of Rising Main pipe line and construction 2 (two) nos. Pump house for Augmentation of Keshiary & its adjoining mouzas W/S Scheme under JJM within Keshiary block under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. within the District of Paschim Medinipur. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),JE3 Kharagpur Sub-division | ORD/000624/2022-2023 | 449/MD | 13/02/2023 | 10/07/2025 | M/S. A.R. ENTERPRISE. | 13.49 | 0 | 0 | 0
20 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. | SM/10124 | Augmentation | Hiring of Bharat Stage- IV/V diesel motor cab (Luxury Taxi) (Standard Non-AC) having contract carriage permit from the regional transport authority for the Office of the Assistant Engineer, Kharagpur Sub- Division, P.H.E. Dte. ( For 12 MONTH )[ Perion fro 23.03.2023 to 22.03.2024] | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE3 Kharagpur Sub-division | ORD/001038/2022-2023 | 342/1/AE/KSD | 23/03/2023 | 23/03/2024 | M/S. SOMNATH | 1.35 | 0 | 0 | 100
21 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. | SM/10124 | Augmentation | Laying of distribution pipeline for left out node and to provide FHTC for Augmentation of Keshiary Piped Water Supply Scheme under Keshiary block within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000097/2024-2025 | 2844/MD | 09/09/2024 | 03/11/2025 | A-PLUS | 59.9 | 0 | 0 | 50
22 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. | SM/10124 | Augmentation | Continuation Work order Hiring of Bharat Stage - IV/VI Diesel Motor Cabs (Standard), having contract Carriage permit from the Regional Transport Authority for the office of the Assistant Engineer, Kharagpur Sub-Division, P.H.E. Dte. for the period (23.09.2024 to 31.12.2024) Vehicle No-WB 05 9394 | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000317/2024-2025 | 519/AE/KSD | 23/09/2024 | 01/01/2025 | M/S. SOMNATH | 0.56 | 0 | 0 | 0
23 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. | SM/10124 | Augmentation | Cleaning the Chokage of pipe in the existing line at Keshiary PWSS under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE3 Kharagpur Sub-division | ORD/000338/2024-2025 | 3581/MD | 06/12/2024 | 05/01/2025 | MAMPI ENTERPRISE | 4.59 | 0 | 0 | 100
Total | [13 empty] | 869.86 | 0 | 0