## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | Amjor Piped Water Supply Scheme. | SM/10318 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations (250 CuM) under Amjor & its adjoining mouzas W/S scheme within Garhbeta-II block in Paschim Medinipur District through Jadavpur University. | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000126/2022-2023 | 1285/MD | 27/06/2022 | 04/07/2022 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 0
2 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | Amjor Piped Water Supply Scheme. | SM/10318 | New | Material Requisition To Resource Division |  |  | RTOR000116/2022-2023 | 245/MD | 18/01/2023 | 18/01/2023 | Resource Division | 17.74 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | Amjor Piped Water Supply Scheme. | SM/10318 | New | Material Requisition To Resource Division |  |  | RTOR000024/2022-2023 | 134/MD | 11/01/2023 | 11/01/2023 | Resource Division | 8.33 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Mechanical | Amjor Piped Water Supply Scheme. | SM/10318 | New | Electric quotation for Amjore PWSS Tube Well-II WS Scheme (Ref. ID 203928706) |  |  | BILL/00399/2022-2023 | Bp-2022-23-148 | 24/03/2023 | 24/03/2023 | WBSEDCL | 0.36 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Mechanical | Amjor Piped Water Supply Scheme. | SM/10318 | New | Electric quotation for Amjore PWSS Tube Well-I WS Scheme (Ref. ID 203928705) |  |  | BILL/00401/2022-2023 | BP-2022-23-149 | 24/03/2023 | 24/03/2023 | WBSEDCL | 0.36 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | Amjor Piped Water Supply Scheme. | SM/10318 | New | Laying distribution pipe line, Construction of Pump House (3.6 mtr X 3.00 mtr.) & Boundary wall including Sinking of 250 X 200 mm dia. X 200 Mtr. depth deep Tube well under JJM with allied work for AMJOR and its adjoining mouzas W/S Scheme in Garhbeta -II Block including supply of all labour & materials within Midnapore Sub-Division under Midnapore Division, PHE Dte. (Part-A) | AE Sadar Sub-division | JE1 Sadar Sub-division,JE2 Sadar Sub-division | ORD/000543/2022-2023 | 2674/MD | 30/12/2022 | 28/02/2023 | ASHIM KUMAR DEY | 169.73 | 76 | 44.77 | 10
7 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | Amjor Piped Water Supply Scheme. | SM/10318 | New | Continuation Work order for Hire charges for hiring of 1 no Motor Cab ( standard ) Commercial with Catalytic Converter attachment with Bharat stage as per prevalent applicable standard compliant new / not old than 30 ( Thirty ) months from the date of 1st. registration on daily hire rate basis for 05 (Five) months only having contract carriage permit for plying with in West Bengal from Regional Transport Authority for the use of the Assistant Engineer ,Midnapore Sadar Sub-Division under Midnapur Division PHE Dte.(Preferably it would be used only the 'Jal Swapna 'Program inaugurated by Honorable C.M) upto 15.07.2023 | AE Sadar Sub-division |  | ORD/000769/2022-2023 | 865/AE/MSSD | 10/02/2023 | 10/07/2023 | SANJIT SINHA | 0.84 | 1.83 | 217.92 | 80
8 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | Amjor Piped Water Supply Scheme. | SM/10318 | New | Construction of R.C.C. Over Head Reservoir of capacity 250 Cum and staging height 20.00 mtr., Pump House (5.40 mtr X 3.60 mtr), Boundary wall including Sinking of 250 X 200 mm dia. X 200 Mtr. depth deep Tube well & FHTC under JJM with allied work for AMJOR & its adjoining mouzas W/S Scheme in Garhbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Part-B) | AE Sadar Sub-division | JE1 Sadar Sub-division,JE2 Sadar Sub-division | ORD/000307/2022-2023 | 1878/MD | 09/09/2022 | 08/03/2023 | ASHIM KUMAR DEY | 152.15 | 78.76 | 51.77 | 30
9 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | Amjor Piped Water Supply Scheme. | SM/10318 | New | Laying of Rising main & interconnection pipeline for Amjor & its adjoining mouzas PWSS, Block - Garhbeta-II, District - Paschim Medinipur under Midnapore Division, PHE Dte. (Length - 675.00 Mtr.) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000052/2024-2025 | 2449/MD | 08/08/2024 | 22/09/2024 | ASHIM KUMAR DEY | 5.41 | 3.13 | 57.73 | 50
10 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Mechanical | Amjor Piped Water Supply Scheme. | SM/10318 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Amjor Piped Water Supply Scheme. under JJM Program under MMD PHE Dte. |  |  | ORD/001374/2022-2023 | 2385/W/MMD | 31/12/2022 | 29/06/2023 | ABHIJIT BASU | 22.88 | 22.68 | 99.14 | 100
11 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | Amjor Piped Water Supply Scheme. | SM/10318 | New | Continuation work order for Hire charges for hiring of 1 no Motor Cab ( standard ) Commercial with Catalytic Converter attachment with Bharat stage as per prevalent applicable standard compliant new / not old than 30 ( Thirty ) months from the date of 1st. registration on daily hire rate basis for 06 ( Six) months only having contract carriage permit for plying with in West Bengal from Regional Transport Authority for the use of the Assistant Engineer ,Midnapore Sadar Sub-Division under Midnapur Division PHE Dte. (period from 01.01.2023 to 30.06.2023) | AE Sadar Sub-division |  | ORD/000768/2022-2023 | 762/AE/MSSD | 30/12/2022 | 30/06/2023 | M/S. ZAMAN ENTERPRISE | 1.01 | 1.98 | 195.18 | 50
12 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | Amjor Piped Water Supply Scheme. | SM/10318 | New | Data Entry Operation for IMIS entry of all information collected during survey work of Schools, Anganwadies Centre, Health Care Institution etc. under Midnapore Division PHE Dte. Period from (15.07.2023 to 14.07.2024) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000185/2023-2024 | 403/AE/MSSD | 14/07/2023 | 14/07/2024 | PULLOCK KUMAR GHOSH | 4.65 | 0 | 0 | 60
Total | [13 empty] | 388.24 | 189.15 | 48.72