## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10648 | New | Quotation Bill of PH-I, Dewanchak water supply scheme under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000158/2022-2023 | 2003978666 | 28/06/2022 | 28/06/2023 | WBSEDCL | 0.11 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10648 | New | Electric quotation BIRSINGHA CCC at Chowka, chowka, Ghatal, T/W-I Pin-721232 |  |  | VCH/002779/2022-2023 |  | 17/11/2022 | 17/11/2022 | WBSEDCL | 0.11 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10648 | New | Electric quotation BIRSINGHA CCC at Gholsai, Chowka, a, Ghatal, T/W-II Pin-721232 |  |  | VCH/002782/2022-2023 |  | 17/11/2022 | 17/11/2022 | WBSEDCL | 0.11 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10648 | New | Electric quotation BIRSINGHA CCC at Gholsai, Chowka, a, Ghatal, T/W-I Pin-721232 |  |  | VCH/002781/2022-2023 |  | 17/11/2022 | 17/11/2022 | WBSEDCL | 0.11 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10648 | New | Electric quotation BIRSINGHA CCC at Chowka, chowka, Ghatal, T/W-II Pin-721232 |  |  | VCH/002780/2022-2023 |  | 17/11/2022 | 17/11/2022 | WBSEDCL | 0.11 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10648 | New | Preparation of D.P.Rs (Consultancy work) in connection with the Proposed Mini Pipe Water Supply Scheme for Mouza- (i) Chauka & (ii) Masarpur under Dewanchak-II Gram Panchayat of SAGY (Sanshad Adarshya Gram Yagona) within Ghatal Block under Midnapore Division, P.H.E. Dte. | AE Ghatal Sub-division |  | ORD/000417/2021-2022 | 1330/MD | 17/08/2021 | 27/08/2021 | RISHAN ENGINEERING CONSULTANCY | 3.46 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10648 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-II under Chowka water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist. Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001240/2022-2023 | 2171/W/MMD | 12/12/2022 | 11/04/2023 | M/S BARMAN ROY TRADERS | 5.93 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10648 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-I under Chowka water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist. Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001239/2022-2023 | 2170/W/MMD | 12/12/2022 | 11/04/2023 | BHABANI PRASAD MANNA | 5.93 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10648 | New | Electric quotation BIRSINGHA CCC at Chowka, chowka, Ghatal, T/W-I Pin-721232 |  |  | BILL/00027/2022-2023 | BP-2022-23-72 | 14/12/2022 | 14/12/2022 | WBSEDCL | 0.11 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10648 | New | Electric quotation BIRSINGHA CCC at Gholsai, Chowka, a, Ghatal, T/W-I Pin-721232 |  |  | BILL/00025/2022-2023 | BP-2022-23-74 | 14/12/2022 | 14/12/2022 | WBSEDCL | 0.11 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10648 | New | Electric quotation BIRSINGHA CCC at Gholsai, Chowka, a, Ghatal, T/W-II Pin-721232 |  |  | BILL/00026/2022-2023 | BP-2022-23-75 | 14/12/2022 | 14/12/2022 | WBSEDCL | 0.11 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10648 | New | Electric quotation BIRSINGHA CCC at Chowka, chowka, Ghatal, T/W-II Pin-721232 |  |  | BILL/00028/2022-2023 | BP-2022-23-73 | 14/12/2022 | 14/12/2022 | WBSEDCL | 0.11 | 0 | 0 | 0
13 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10648 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Chauka (Zone-II), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. |  |  | BILL/00724/2022-2023 | BP-2022-23-661 | 29/03/2023 | 29/03/2023 | M/S. D.K.H.CONSTRUCTION | 3.05 | 0 | 0 | 0
14 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10648 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Chauka (Zone-I), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Ghatal) | ORD/000210/2022-2023 | 1675/MD | 12/08/2022 | 09/01/2023 | M/S. D.K.H.CONSTRUCTION | 39.56 | 0 | 0 | 91
15 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10648 | New | Material Requisition To Resource Division |  |  | RTOR000042/2024-2025 | 3351/MD | 25/11/2024 | 25/11/2024 | Resource Division | 2.67 | 0 | 0 | 0
16 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Chauka mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10648 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Chauka (Zone-II), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Ghatal) | ORD/000211/2022-2023 | 1676/MD | 12/08/2022 | 31/12/2024 | M/S. D.K.H.CONSTRUCTION | 45.86 | 0 | 0 | 91
Total | [13 empty] | 107.42 | 0 | 0