## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Sabang | Central Drilling | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. | SM/10649 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 190 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR KRISHNAPRIYA W/S SCH (TW-II), PINGLA BLOCK UNDER PASCHIM MEDINIPUR DISTRICT, CDD, PHE DTE. |  |  | ORD/000227/2022-2023 | 16/CDD | 04/04/2022 | 04/05/2022 | MENAKA ENTERPRISE | 9.32 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. | SM/10649 | New | Preparation of D.P.R (Consultancy work) in connection with the Proposed Pipe Water Supply Scheme for Dashagram & its adjoining mouza within Sabang Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/000439/2021-2022 | 1691/MD | 30/09/2021 | 10/10/2021 | GOBINDA MAITY | 2.74 | 2.25 | 82.25 | 0
3 | PASCHIM MEDINIPUR | Sabang | Central Drilling | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. | SM/10649 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (2522MM X 150MM X 190 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR DASHAGRAM W/S SCH (TW-II), PINGLA BLOCK UNDER PASCHIM MEDINIPUR DISTRICT, CDD, PHE DTE. |  |  | ORD/000246/2022-2023 | 16/ CDD | 04/04/2022 | 04/05/2022 | MENAKA ENTERPRISE | 9.32 | 8.57 | 91.93 | 0
4 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. | SM/10649 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001309/2022-2023 | 2311/W/MMD | 29/12/2022 | 27/06/2023 | KAMAKSHYA ENTERPRISE | 25.14 | 22.55 | 89.71 | 0
5 | PASCHIM MEDINIPUR | Sabang | Central Drilling | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. | SM/10649 | New | Providing TW materials conforming to IS: 12818:2010 with other works at site for construction of TW in Dasha Gram PWSS under CDD, PHE Dte. |  |  | ORD/000334/2022-2023 | 579/CMSD-I | 30/11/2022 | 07/12/2022 | MENAKA ENTERPRISE | 0.98 | 0.55 | 55.64 | 0
6 | PASCHIM MEDINIPUR | Sabang | Central Drilling | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. | SM/10649 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 160 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR DASAGRAM W/S SCH (TW-II), PASCHIM MIDNAPORE DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000327/2022-2023 | 1455/CDD | 30/11/2022 | 30/12/2022 | MENAKA ENTERPRISE | 9.3 | 8.59 | 92.34 | 0
7 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. | SM/10649 | New | Material Requisition To Resource Division |  |  | RTOR000026/2022-2023 | 137/MD | 11/01/2023 | 11/01/2023 | Resource Division | 15.83 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. | SM/10649 | New | Material Requisition To Resource Division |  |  | RTOR000143/2022-2023 | 514/MD | 20/02/2023 | 20/02/2023 | Resource Division | 28.24 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. | SM/10649 | New | Material Requisition To Resource Division |  |  | RTOR000002/2023-2024 | 940/MD | 05/04/2023 | 05/04/2023 | Resource Division | 28.23 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. | SM/10649 | New | Electric quotation for Dasagram PWSS Tube Well-II in connection Chandkuri CCC ( Consumer No. 2004164613) |  |  | BILL/00051/2022-2023 | BP-2022-23-101 | 18/01/2023 | 18/01/2023 | WBSEDCL | 2.47 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. | SM/10649 | New | Electric quotation for Dasagram PWSS Tube Well-I near Hospital in connection Chandkuri CCC (Consumer No. 2004164602) |  |  | BILL/00052/2022-2023 | BP-2022-23-102 | 30/01/2023 | 30/01/2023 | WBSEDCL | 2.41 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. | SM/10649 | New | Laying distribution pipe line, soil test & construction of R.C.C. Over Head Reservoir of capacity 400 Cum (Intze type with Pile Foundation) and staging height 20.00 mtr. & FHTC under JJM with allied work for Dasha Gram and its adjoining mouzas W/S Scheme in Sabang Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000372/2022-2023 | 1956/MD | 20/09/2022 | 14/03/2026 | M/S. A.R. ENTERPRISE. | 512.44 | 331.64 | 64.72 | 60
13 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. | SM/10649 | New | Laying of Rising Main including Interconnection, Construction of Pump House & Boundary wall for Dasha Gram & its adjoining mouzas W/S Scheme in Sabang block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000615/2022-2023 | 441/MD | 10/02/2023 | 26/04/2026 | M/S. A.R. ENTERPRISE. | 44.01 | 8.35 | 18.98 | 20
Total | [13 empty] | 690.46 | 382.51 | 55.4