## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Daspur mouzas, Block - Sabang, District - Paschim Medinipur | SM/10658 | New | Electric quotation Sabang CCC at Daspur, Bankibheri Pin-721434 | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001590/2021-2022 | 2003870026 | 23/03/2022 | 23/03/2023 | WBSEDCL | 0.13 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Daspur mouzas, Block - Sabang, District - Paschim Medinipur | SM/10658 | New | Electric Quotation bill Sabang CCC at Daspur, Bankibheri, Pin-721434 |  |  | VCH/002768/2022-2023 |  | 17/11/2022 | 17/11/2022 | WBSEDCL | 0.13 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Daspur mouzas, Block - Sabang, District - Paschim Medinipur | SM/10658 | New | Sinking of (150 mmX 100 mmX 150mtr) RBTW by Rotary Method at Daspur water supply scheme, tube well no. 1 of Sabang Block of Paschim Midnapur District under Midnapur Mechanical Division P.H.E Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001285/2021-2022 | 75/W/MMD | 17/01/2022 | 22/01/2022 | DEBJYOTI BASU | 4.47 | 0 | 0 | 100
4 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Daspur mouzas, Block - Sabang, District - Paschim Medinipur | SM/10658 | New | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at DASPUR water supply scheme, tube well no. 2 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. |  | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001282/2021-2022 | 76/W/MMD | 17/01/2022 | 22/01/2022 | DEBJYOTI BASU | 4.47 | 0 | 0 | 100
5 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Daspur mouzas, Block - Sabang, District - Paschim Medinipur | SM/10658 | New | Additional work in connection with sinking of (150mmX100mmX150mtr) RBTW by Rotary method at Daspur water supply scheme, tube well no.-1 of Sabang Block of PaschimMidnapur Dist. under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001556/2021-2022 | 175/MMSD-I | 17/02/2022 | 24/02/2022 | DEBJYOTI BASU | 0.35 | 0 | 0 | 80
6 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Daspur mouzas, Block - Sabang, District - Paschim Medinipur | SM/10658 | New | QUOTATION FOR NEW POWER CONNECTION OF DASPUR MINI WATER SUPPLY ASCHEME [ APPLICATION --2004478402, REFERENCE ID ----204120945, SABONG CCC, QUOTATION NO ---2004478402/QUOT/03 DATED 26/10/2023, SCHEME NAME --- DASPUR MINI. , SCHEME CODE ---SM/10658 , MB NO--3580 ] |  |  | BILL/02891/2023-2024 | BP-2023-24-344 | 10/11/2023 | 10/11/2023 | WBSEDCL | 3.98 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Daspur mouzas, Block - Sabang, District - Paschim Medinipur | SM/10658 | New | Electric quotation Sabang CCC at Daspur, Bankibheri Pin-721434 ( 2003870026) |  |  | BILL/00158/2022-2023 | BP-2022-23-123 | 09/03/2023 | 09/03/2023 | WBSEDCL | 0.12 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Daspur mouzas, Block - Sabang, District - Paschim Medinipur | SM/10658 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Daspur (Zone-I), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000464/2022-2023 | 2184/MD | 01/11/2022 | 31/03/2023 | S.N ENTERPRISE | 35.12 | 0 | 0 | 80
9 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Daspur mouzas, Block - Sabang, District - Paschim Medinipur | SM/10658 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well-II at Daspur, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000017/2022-2023 | 558/W/MMD | 12/04/2022 | 07/02/2025 | SUBHAM ENTERPRISE | 6.44 | 0 | 0 | 100
10 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Daspur mouzas, Block - Sabang, District - Paschim Medinipur | SM/10658 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well-I at Daspur, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000016/2022-2023 | 557/W/MMD | 12/04/2022 | 10/08/2022 | RITESH ENTERPRISE | 6.49 | 0 | 0 | 100
11 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Daspur mouzas, Block - Sabang, District - Paschim Medinipur | SM/10658 | New | Restoration of damaged distribution system and other allied works in different locations of Single Village W/S Schemes (SVS) within Sabang Block under Midnapore Division P.H.E. Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang Blk) | ORD/000477/2024-2025 | 480/MD | 13/02/2025 | 14/04/2025 | A-PLUS | 22 | 0 | 0 | 100
12 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Daspur mouzas, Block - Sabang, District - Paschim Medinipur | SM/10658 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Daspur (Zone-II), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000465/2022-2023 | 2185/MD | 01/11/2022 | 01/04/2025 | S.T. ENTERPRISE | 37.32 | 0 | 0 | 80
Total | [13 empty] | 121.04 | 0 | 0