## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Sartla (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10685 | Augmentation | Restoration of pipe line damaged due to construction of PMGSY roads, village Roads over existing pipe line Sartla & its adjoining mouzas (Rampura, Kororda, Cheena) W/S Scheme at Sabang Block under Kharagpur Sub Division within Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE3 Kharagpur Sub-division | ORD/000489/2021-2022 | 2182/MD | 17/12/2021 | 31/01/2022 | GOBINDA MAITY | 43.21 | 18 | 41.65 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Sartla (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10685 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Sartla PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/000438/2021-2022 | 1676/MD | 29/09/2021 | 09/10/2021 | SIRCON ENGINEERING SERVICES PVT. LTD. | 2.23 | 2.2 | 98.84 | 100
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Sartla (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10685 | Augmentation | Rejuvenation of Ground water based piped water supply scheme for Sartla (Part) to Accommodate FHTC under JJM under Sabang Block in Paschim Medinipur Districct Under Medinipur Division PHE Dte. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE3 Kharagpur Sub-division | ORD/000184/2022-2023 | 1479/MD | 25/07/2022 | 08/09/2022 | GOBINDA MAITY | 61.29 | 54.01 | 88.13 | 100
4 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Sartla (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10685 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Sartla (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002043/2022-2023 | 951/W/MMD | 28/03/2023 | 24/09/2023 | EMCON | 10.78 | 5.66 | 52.53 | 98
5 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Sartla (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10685 | Augmentation | Supply and delivery at site Submersible pumping machinery and other electro-mechanical equipment in connection with Rejuvenation of Ground water based piped piped water supply scheme for PH No III of Sartla Part to accommodate FHTC under Sabang Block in Paschim Medinipur District under M.M.D,.PH.E. DTE.TSM009946 | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000240/2023-2024 | 605/MMSD-I | 06/06/2023 | 21/06/2023 | EMCON | 5.76 | 5.76 | 100 | 100
6 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Sartla (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10685 | Augmentation | QUOTATION MONEY FOR ADDITIONAL TUBEWELL NO 3 OF SARTLA WATER SUPPLY SCHEME [ REFERENCE ID 860268179, APLLICATION ID 100000077609 , CHANDKURI CCC, WBSEDCL ] |  |  | BILL/00120/2023-2024 | BP-2023-24-44 | 19/05/2023 | 19/05/2023 | WBSEDCL | 0.78 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Sartla (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10685 | Augmentation | Service Connection charges of WBSEDL at Sartla Additional TW-III W/S Scheme (Consumer No. 2004156120) |  |  | BILL/00043/2022-2023 | BP-2022-23-91 | 04/01/2023 | 04/01/2023 | WBSEDCL | 3.81 | 0 | 0 | 0
Total | [13 empty] | 127.86 | 85.64 | 66.98