## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Krishnaballabhpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10717 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Mini Piped Water Supply Scheme for Krishnaballabhpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001313/2022-2023 | 2315/W/MMD | 29/12/2022 | 27/06/2023 | M/S EMMESS | 6.01 | 5.97 | 99.33 | 80
2 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Krishnaballabhpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10717 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Krishnaballabhpur, Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Ghatal) | ORD/000594/2022-2023 | 345/MD | 31/01/2023 | 31/12/2024 | M/S. SOMNATH | 43.6 | 32.63 | 74.84 | 90
3 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Krishnaballabhpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10717 | New | Service Connection charges of WBSEDCL at Krishnaballavpur P/H-I |  |  | BILL/00036/2022-2023 | BP-2022-23-95 | 11/01/2023 | 11/01/2023 | WBSEDCL | 0.13 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Krishnaballabhpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/10717 | New | Material Requisition To Resource Division |  |  | RTOR000045/2024-2025 | 3354/MD | 25/11/2024 | 25/11/2024 | Resource Division | 1.15 | 0 | 0 | 0
Total | [13 empty] | 50.89 | 38.6 | 75.85