## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Khasbazar (Part) to accommodate FHTC under Jal Sapno Mission under Debra block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10731 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Khasbazar PWSS within Debra Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/000434/2021-2022 | 1667/MD | 28/09/2021 | 08/10/2021 | RISHAN ENGINEERING CONSULTANCY | 2.28 | 0 | 0 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Khasbazar (Part) to accommodate FHTC under Jal Sapno Mission under Debra block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10731 | Augmentation | Electric quotation for KHASBAZAR Water Supply Scheme T/W-(Ref. ID - 204024556) |  |  | BILL/00545/2023-2024 | BP-2023-24-288 | 31/08/2023 | 31/08/2023 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 4.53 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Khasbazar (Part) to accommodate FHTC under Jal Sapno Mission under Debra block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10731 | Augmentation | Rejuvenation of Ground Water Based Water Supply Scheme of Khasbazar (Part) to accommodate FHTC under JJM within Debra Dev. Block under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. Dist. Paschim Medinipur. | AE Kharagpur Sub-division |  | ORD/000185/2022-2023 | 1484/MD | 26/07/2022 | 24/09/2022 | SHAKEEL KHAN | 57.44 | 0 | 0 | 100
4 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Khasbazar (Part) to accommodate FHTC under Jal Sapno Mission under Debra block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10731 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Khasbazar (Part) to accommodate FHTC under Jal Sapno Mission under Debra block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002004/2022-2023 | 875/W/MMD | 27/03/2023 | 23/09/2023 | RADHARANI ENTERPRISE | 5.98 | 0 | 0 | 100
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Khasbazar (Part) to accommodate FHTC under Jal Sapno Mission under Debra block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10731 | Augmentation | Cleaning the Chokage of pipe in the existing line at Khasbazar PWSS under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. | AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | ORD/000312/2024-2025 | 3405/MD | 25/11/2024 | 16/12/2024 | SUBRATA DAS | 4.53 | 0 | 0 | 100
Total | [13 empty] | 74.77 | 0 | 0