## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10821 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Chandkuri PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/000430/2021-2022 | 1662/MD | 28/09/2021 | 08/10/2021 | SIRCON ENGINEERING SERVICES PVT. LTD. | 2.33 | 0 | 0 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10821 | Augmentation | Restoration of pipe line damaged due to construction of concrete road at Kholageria village & excess length of pipe in connection with FHTC work at Chandkuri (Zone I) W/S Scheme at Sabang Block under Kharagpur Sub-Division within Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/000078/2022-2023 | 1067/MD | 03/06/2022 | 24/06/2022 | DULAL CHANDRA DAS | 19.68 | 0 | 0 | 80
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10821 | Augmentation | Restoration of pipe line damaged due to construction of road at Chandkuri market & excess pipeline in connection with FHTC work at Chandkuri (Zone II) W/S Scheme at Sabang Block under Kharagpur Sub-Division within Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/000079/2022-2023 | 1068/MD | 03/06/2022 | 24/06/2022 | DULAL CHANDRA DAS | 24.23 | 0 | 0 | 80
4 | PASCHIM MEDINIPUR |  | Central Drilling | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10821 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 170 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR CHANDKURI W/S SCH (Z-II), PASCHIM MIDNAPORE DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000328/2022-2023 | 1778/CDD | 02/01/2023 | 01/02/2023 | MENAKA ENTERPRISE | 10.15 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10821 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002243/2022-2023 | 186/MMSD-I | 27/02/2023 | 30/08/2023 | M/S BIKASH DE | 0.9 | 0 | 0 | 25
6 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10821 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002284/2022-2023 | 187/MMSD-I | 27/02/2023 | 30/08/2023 | SUBHASIS ROY | 0.9 | 0 | 0 | 100
7 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10821 | Augmentation | Replacement and upgradation work of Voltage Stabilizer for Tube well No. III of Chandkuri Zone I Water Supply Scheme Block Sabang under MMD, PHE Dte. Dist.- Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001301/2023-2024 | 1226/MMSD-I | 03/10/2023 | 02/11/2023 | BALAJI CONSTRUCTION | 3.6 | 0 | 0 | 100
8 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10821 | Augmentation | Service Connection charges of WBSEDCL for T/W-III of Zone-I of Chandkuri W/S Scheme (Consumer No. 2004156096) |  |  | BILL/00048/2022-2023 | BP-2022-23-93 | 10/01/2023 | 10/01/2023 | WBSEDCL | 2.2 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10821 | Augmentation | Service Connection charges of WBSEDCL for Additional T/W-III of Zone-II of Chandkuri W/S Scheme (Consumer No. 2004156140) |  |  | BILL/00047/2022-2023 | BP-2022-23-92 | 04/01/2023 | 04/01/2023 | WBSEDCL | 2.41 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR |  | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10821 | Augmentation | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Zone-I) (Part) to Accommodate FHTC under JJM at Sabang Block in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000206/2022-2023 | 1671/MD | 12/08/2022 | 26/09/2022 | DULAL CHANDRA DAS | 44.9 | 0 | 0 | 80
11 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10821 | Augmentation | SUPPLY AND DELIVERY OF FUEL FOR INSPECTION VEHICAL FOR INSPECTION OF JJM WORK AT OFFICE OF THE ASSISTANT ENGINEER MMSD1 | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002279/2022-2023 | 186./MMSD-I | 27/02/2023 | 30/08/2023 | M/S BIKASH DE | 3 | 0 | 0 | 100
12 | PASCHIM MEDINIPUR |  | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10821 | Augmentation | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Zone-II) (Part) to Accommodate FHTC under JJM at Sabang Block in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000207/2022-2023 | 1672/MD | 12/08/2022 | 26/09/2022 | DULAL CHANDRA DAS | 50.82 | 0 | 0 | 100
13 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10821 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Additional Tube Well-III, Zone-I of Chandkuri to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000129/2023-2024 | 1349/W/MMD | 24/05/2023 | 20/11/2023 | M/S EMMESS | 11.88 | 0 | 0 | 100
14 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10821 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001307/2022-2023 | 2309/W/MMD | 29/12/2022 | 27/06/2023 | BALAJI CONSTRUCTION | 10.79 | 0 | 0 | 100
Total | [13 empty] | 187.8 | 0 | 0