## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10839 | Augmentation | Conducting of Route Survey and allied works in connection with the Functional Household Tap Connection of existing PWSS (Mohanpur, Block - Mohanpur) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000214/2021-2022 | 1136/MD | 16/07/2021 | 26/07/2021 | SIRCON ENGINEERING SERVICES | 3.04 | 0 | 0 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10839 | Augmentation | Design of Distribution Network and preparation of DPR in connection with the Functional Household Tap Connection of existing PWSS (Mohanpur, Block - Mohanpur) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000215/2021-2022 | 1144/MD | 19/07/2021 | 29/07/2021 | SIRCON ENGINEERING SERVICES | 3.49 | 0 | 0 | 100
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10839 | Augmentation | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Kashida & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) |  | ORD/000100/2022-2023 | 752/MD | 22/04/2022 | 12/05/2022 | ENVIROTECH SOLUTIONS | 7.87 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10839 | Augmentation | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Sautia & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000102/2022-2023 | 754/MD | 22/04/2022 | 12/05/2022 | ENVIROTECH SOLUTIONS | 6.68 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10839 | Augmentation | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Borai & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000101/2022-2023 | 753/MD | 22/04/2022 | 12/05/2022 | ENVIROTECH SOLUTIONS | 5.24 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10839 | Augmentation | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Jarisai & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000103/2022-2023 | 755/MD | 22/04/2022 | 12/05/2022 | ENVIROTECH SOLUTIONS | 6.63 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10839 | Augmentation | Continuation Work Order for the work of Laying Balance (Part) Distribution System to accommodate FHTC of Proposed Augmentation Pipe Water Supply Scheme for Mohanpur & its adjoining Mouzas, Block: - Mohanpur, District: - Paschim Midnapore. (Total Length = 18,000.00 Mtr.) | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000610/2022-2023 | 382/MD | 03/02/2023 | 04/04/2023 | GOBINDA MAITY | 87.47 | 0 | 0 | 79
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10839 | Augmentation | Sinking of 1 (One) no. 250 X 150 mm dia. X 200 mtr. Depth deep tube well by direct rotary method for Augmentation of Mohanpur W/S Scheme within Mohanpur Block under Midnapore Division, P.H.E. Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000621/2022-2023 | 446/MD | 13/02/2023 | 23/02/2023 | GOBINDA MAITY | 11.7 | 0 | 0 | 100
9 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10839 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000171/2023-2024 | 1363/MD | 02/05/2023 | 02/05/2023 | Resource Division | 61.09 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10839 | Augmentation | Electrict Quotation Bill for mohanpur water supply scheme (consumer ID-203995501) |  |  | BILL/00339/2023-2024 | BP-2023-24-228 | 05/09/2023 | 05/09/2023 | WBSEDCL | 2.3 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10839 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001966/2022-2023 | 877/W/MMD | 27/03/2023 | 23/09/2023 | JOYSHREE CONCERN | 11.85 | 0 | 0 | 51
12 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10839 | Augmentation | Laying Distribution pipe line, Soil test & Construction of R.C.C. Over Head Reservoir of capacity 550 Cum (Pile foundation) and staging height 20.00 mtr. & FHTC under JJM with allied work for Augmentation of Mohanpur and its adjoining mouzas W/S scheme in Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),JE3 Kharagpur Sub-division | ORD/000378/2022-2023 | 1961/MD | 20/09/2022 | 27/11/2025 | GOBINDA MAITY | 658.99 | 0 | 0 | 95
Total | [13 empty] | 866.34 | 0 | 0