## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10842 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Barsahara PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/000425/2021-2022 | 1657/MD | 28/09/2021 | 08/10/2021 | SIRCON ENGINEERING SERVICES PVT. LTD. | 2.14 | 2.13 | 99.6 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10842 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002243/2022-2023 | 186/MMSD-I | 27/02/2023 | 30/08/2023 | M/S BIKASH DE | 0.9 | 0.06 | 6.68 | 25
3 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10842 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002284/2022-2023 | 187/MMSD-I | 27/02/2023 | 30/08/2023 | SUBHASIS ROY | 0.9 | 0.09 | 10 | 100
4 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10842 | Augmentation | Service connection charges of WBSEDCL at TW-III (Additional) of Barasahara Water Supply Scheme (Ref. ID - 20395154) |  |  | BILL/00408/2022-2023 | BP-2022-23-152 | 28/03/2023 | 28/03/2023 | WBSEDCL | 3.4 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10842 | Augmentation | Electric quotation for Barsahara PWSS Tube Well-III WS Scheme (Ref. ID 203935154) |  |  | BILL/00414/2022-2023 |  | 25/03/2023 | 25/03/2023 | WBSEDCL | 3.4 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10842 | Augmentation | Service connection charges of WBSEDCL at TW-IV (Additional) of Barasahara Water Supply Scheme (Ref. ID - 203934601) |  |  | BILL/00409/2022-2023 |  | 22/03/2023 | 22/03/2023 | WBSEDCL | 2.55 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10842 | Augmentation | Electric quotation for Barsahara PWSS Tube Well-IV WS Scheme (Ref. ID 203934601) |  |  | BILL/00413/2022-2023 | BP-2002-23-153 | 28/03/2023 | 28/03/2023 | WBSEDCL | 2.55 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10842 | Augmentation | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under JJM at Sabang Block in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000331/2022-2023 | 1892/MD | 12/09/2022 | 11/11/2022 | DULAL CHANDRA DAS | 50.39 | 49.21 | 97.67 | 50
9 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10842 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001306/2022-2023 | 2308/W/MMD | 29/12/2022 | 27/06/2023 | RITESH ENTERPRISE | 10.79 | 0 | 0 | 85
10 | PASCHIM MEDINIPUR |  | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10842 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House for Sansahara & Manikarah villages within Barsahara PWSS in Sabang Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000665/2022-2023 | 584/MD | 23/02/2023 | 24/04/2023 | DULAL CHANDRA DAS | 17.7 | 7.13 | 40.29 | 10
11 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10842 | Augmentation | Supply and Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring at Tube Well no 4 of Barshahara Water Supply Scheme (Block- Sabang) under MMD, PHE Dte., Dist. Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000492/2023-2024 | 1850/W/MMD | 22/08/2023 | 29/06/2025 | MANORANJAN DEY | 12.51 | 11.77 | 94.07 | 100
12 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/10842 | Augmentation | Supply and Installation of Voltage Stabilizer for Tube well No.-3 of Barshahara Water Supply Scheme [ Block-Sabang] under MMD, PHE Dte., Dist.- Paschim Medinipur. (JJM Work) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001252/2023-2024 | 1112/MMSD-I | 14/09/2023 | 14/10/2023 | RITESH ENTERPRISE | 2.83 | 2.83 | 100 | 100
Total | [13 empty] | 110.05 | 73.22 | 66.54