## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Division | Sabra Piped Water Supply Scheme. | SM/11460 | New | Continuation Work Order for the work of Laying Balance Distribution System to accommodate FHTC of Proposed Pipe Water Supply Scheme for Sabra & its adjoining Mouzas, Block: - Dantan-II, District: - Paschim Midnapore. (Total Length = 15,893.00 Mtr.) | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II) | ORD/000663/2022-2023 | 676/MD | 02/03/2023 | 01/05/2023 | GOBINDA MAITY | 78.34 | 68.05 | 86.87 | 0
2 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Division | Sabra Piped Water Supply Scheme. | SM/11460 | New | Material Requisition To Resource Division |  |  | RTOR000123/2022-2023 | 336/MD | 31/01/2023 | 31/01/2023 | Resource Division | 84.48 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Division | Sabra Piped Water Supply Scheme. | SM/11460 | New | Material Requisition To Resource Division |  |  | RTOR000096/2023-2024 | 1285/MD | 28/04/2023 | 28/04/2023 | Resource Division | 22.66 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Mechanical | Sabra Piped Water Supply Scheme. | SM/11460 | New | Electric Quotiaton for New S.C. Sabra Water Supply Scheme PH-III (Ref. ID-203964024) |  |  | BILL/00070/2023-2024 | BP-2023-24-12 | 27/04/2023 | 27/04/2023 | WBSEDCL | 0.58 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Mechanical | Sabra Piped Water Supply Scheme. | SM/11460 | New | Electric Quotiaton for New S.C (Infra. Cost.). Sabra Water Supply Scheme PH-III (Ref. ID-860267635) |  |  | BILL/00071/2023-2024 | BP-2023-24-13 | 27/04/2023 | 27/04/2023 | WBSEDCL | 3.51 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Mechanical | Sabra Piped Water Supply Scheme. | SM/11460 | New | Extra work due to way leave at Sabra T.W.No-III |  |  | BILL/00579/2023-2024 | BP-2023-24-131 | 19/07/2023 | 19/07/2023 | WBSEDCL | 0.95 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Mechanical | Sabra Piped Water Supply Scheme. | SM/11460 | New | Electric Quotiaton for New S.C.Sabra Water Supply Scheme PH-II (Ref. ID-203964023) |  |  | BILL/00068/2023-2024 | BP-2023-24-10 | 27/04/2023 | 27/04/2023 | WBSEDCL | 0.58 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Mechanical | Sabra Piped Water Supply Scheme. | SM/11460 | New | Electric Quotiaton for New S.C. Sabra Water Supply Scheme PH-I (Ref. ID-203964025) |  |  | BILL/00066/2023-2024 | BP-2023-24-8 | 27/04/2023 | 27/04/2023 | WBSEDCL | 0.58 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Mechanical | Sabra Piped Water Supply Scheme. | SM/11460 | New | Electric Quotiaton for New S.C (Infra. Cost.). Sabra Water Supply Scheme PH-II (Ref. ID-860267634) |  |  | BILL/00069/2023-2024 | BP-2023-24-11 | 27/04/2023 | 27/04/2023 | WBSEDCL | 2.23 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Mechanical | Sabra Piped Water Supply Scheme. | SM/11460 | New | Electric Quotiaton for New S.C (Infra. Cost.). Sabra Water Supply Scheme PH-I (Ref. ID-860267633) |  |  | BILL/00067/2023-2024 | BP-2023-24-9 | 27/04/2023 | 27/04/2023 | WBSEDCL | 2.19 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Mechanical | Sabra Piped Water Supply Scheme. | SM/11460 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Sabra Piped Water Supply Scheme.under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000019/2023-2024 | 1157/W/MMD | 17/04/2023 | 14/10/2023 | PS & ASSOCIATES | 27.3 | 13.37 | 48.97 | 60
12 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Division | Sabra Piped Water Supply Scheme. | SM/11460 | New | Laying of Rising Main including interconnection for Sabra and its adjoining mouzas Water Supply Scheme within Dantan-II Block under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II) | ORD/000639/2023-2024 | 139/MD | 18/01/2024 | 17/02/2024 | GOBINDA MAITY | 8.07 | 0 | 0 | 0
13 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Mechanical | Sabra Piped Water Supply Scheme. | SM/11460 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SABRA AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000002/2023-2024 | 1104/W/MMD | 05/04/2023 | 02/10/2023 | P.K.ENGINEERING | 27.37 | 27.02 | 98.72 | 100
14 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Division | Sabra Piped Water Supply Scheme. | SM/11460 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 600 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for Sabra & its adjoining mouzas W/S Scheme in Datan-II block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),JE3 Kharagpur Sub-division | ORD/000478/2022-2023 | 2273/MD | 09/11/2022 | 26/05/2026 | GOBINDA MAITY | 608.66 | 474.91 | 78.02 | 94
Total | [13 empty] | 867.51 | 583.35 | 67.24