## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. | SM/11622 | New | Construction of M.S. Fabricated and R.C.C Supporting Structure including aligning pipe line in connection of laying distribution main of Jote Kanuramgarh & Ranichak Water supply scheme under Midnapore Division P.H.E. Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000628/2022-2023 | 453/MD | 13/02/2023 | 14/04/2023 | GOBINDA MAITY | 50.85 | 29.04 | 57.11 | 60
2 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. | SM/11622 | New | Material Requisition To Resource Division |  |  | RTOR000169/2022-2023 | 904/MD | 31/03/2023 | 31/03/2023 | Resource Division | 40.66 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. | SM/11622 | New | Material Requisition To Resource Division |  |  | RTOR000145/2022-2023 | 516/MD | 20/02/2023 | 20/02/2023 | Resource Division | 40.67 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. | SM/11622 | New | Electric quotation for tw-II of Jote kanuramgarh w/s scheme(consumar ID-203974597) |  |  | BILL/00101/2023-2024 | BP-2023-24-17 | 28/04/2023 | 28/04/2023 | WBSEDCL | 4.14 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. | SM/11622 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. |  |  | BILL/00722/2022-2023 | 2022-23-780-781 | 29/03/2023 | 29/03/2023 | GOBINDA MAITY | 28.72 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. | SM/11622 | New | Electric quotation for tw-I of Jotekanuramgarh w/s scheme (consumar ID-203974593) |  |  | BILL/00100/2023-2024 | BP-2023-24-18 | 28/04/2023 | 28/04/2023 | WBSEDCL | 7.05 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. | SM/11622 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. |  |  | BILL/00720/2022-2023 | 22-23-707,8,9 | 13/03/2023 | 13/03/2023 | GOBINDA MAITY | 61 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. | SM/11622 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. |  |  | BILL/00721/2022-2023 | 2022-23-723,24 | 20/03/2023 | 20/03/2023 | GOBINDA MAITY | 4.92 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. | SM/11622 | New | Preliminarily ground protection works (i.e. Driving Eucalyptus Bullah Piles, Land Development etc.) in connection with Construction of R.C.C. OHR at Head Works site of Jote Kanuramgar W/S Scheme under Midnapore Division, PHE Dte. (Total Length of Double row piling works @ 500 C/C = 100.00 Mtr.) | AE Ghatal Sub-division |  | ORD/000070/2024-2025 | 2662/MD | 29/08/2024 | 28/09/2024 | GOBINDA MAITY | 18.98 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. | SM/11622 | New | Material Requisition To Resource Division |  |  | RTOR000025/2024-2025 | 3344/MD | 25/11/2024 | 25/11/2024 | Resource Division | 18.02 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. | SM/11622 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000499/2022-2023 | 2364/MD | 21/11/2022 | 16/04/2026 | GOBINDA MAITY | 1460.37 | 171.02 | 11.71 | 58
12 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. | SM/11622 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001311/2022-2023 | 2313/W/MMD | 29/12/2022 | 18/12/2024 | DEBJYOTI BASU | 25.25 | 12.6 | 49.88 | 100
13 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. | SM/11622 | New | Laying of Rising main including interconnection of Jote Kanuramgarh & its adjoining mouzas W/S Scheme under Daspur-II block within Ghatal Sub-Division of Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000021/2024-2025 | 2051/MD | 02/07/2024 | 21/04/2025 | M/S PIJUSH PAL | 5.92 | 0 | 0 | 100
Total | [13 empty] | 1766.55 | 212.65 | 12.04