## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. | SM/11623 | New | Material Requisition To Resource Division |  |  | RTOR000146/2022-2023 | 517/MD | 20/02/2023 | 20/02/2023 | Resource Division | 16.87 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. | SM/11623 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. |  |  | BILL/00720/2022-2023 | 22-23-707,8,9 | 13/03/2023 | 13/03/2023 | GOBINDA MAITY | 61 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. | SM/11623 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. |  |  | BILL/00722/2022-2023 | 2022-23-780-781 | 29/03/2023 | 29/03/2023 | GOBINDA MAITY | 28.72 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. | SM/11623 | New | Electric Quotation for TW-II of Ramkrishnapur W/S Scheme (ID-203974545) |  |  | BILL/00096/2023-2024 | BP-2023-24-21 | 28/04/2023 | 28/04/2023 | WBSEDCL | 3.11 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. | SM/11623 | New | Electric Quotation for TW-I of Ramkrishapur W/S Scheme (ID-203973517) |  |  | BILL/00095/2023-2024 | BP-2023-24-22 | 28/04/2023 | 28/04/2023 | WBSEDCL | 5.24 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. | SM/11623 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. |  |  | BILL/00721/2022-2023 | 2022-23-723,24 | 20/03/2023 | 20/03/2023 | GOBINDA MAITY | 4.92 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. | SM/11623 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001312/2022-2023 | 2314/W/MMD | 29/12/2022 | 27/06/2023 | SUJOY RANJAN BHOWMICK | 27.35 | 27.01 | 98.75 | 80
8 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. | SM/11623 | New | Additional work for increasing of hight of tube well and other allied work ar tube well no. I & II of Ramkrishnapur and Kanchangeria (Tube well no. I) water supply scheme [Block-Daspur-II and Debra] under MMD, PHE Dte., Dist.- Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002709/2023-2024 | 338/MMSD-I | 05/03/2024 | 15/03/2024 | SUJOY RANJAN BHOWMICK | 1.33 | 0 | 0 | 100
9 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. | SM/11623 | New | Material Requisition To Resource Division |  |  | RTOR000026/2024-2025 | 3345/MD | 25/11/2024 | 25/11/2024 | Resource Division | 10.33 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. | SM/11623 | New | Supply & Delivery of DI Specials for laying of Rising Main & distribution system including interconnection for Ramkrishnapur and its adjoining mouzas Water Supply Scheme within Daspur-II Block under Ghatal Sub Division of Midnapore Division, P.H.E.Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II),JE1 Ghatal Sub-division | ORD/000457/2023-2024 | 799/AE/GSD | 10/11/2023 | 17/11/2023 | GOBINDA MAITY | 1.26 | 0 | 0 | 100
11 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. | SM/11623 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000499/2022-2023 | 2364/MD | 21/11/2022 | 16/04/2026 | GOBINDA MAITY | 1460.37 | 244.07 | 16.71 | 58
12 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. | SM/11623 | New | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001562/2023-2024 | 1211/MMSD-I | 29/09/2023 | 30/12/2023 | SUBHASIS ROY | 0.45 | 0 | 0 | 0
13 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. | SM/11623 | New | Laying of Rising main including interconnection of Ramkrishnapur and its adjoining mouzas Water Supply Scheme under Daspur-II Block under Ghatal Sub-Division within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000717/2023-2024 | 143/MD | 18/01/2024 | 07/02/2024 | GOBINDA MAITY | 6.05 | 0 | 0 | 100
14 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. | SM/11623 | New | Laying additional distribution system pipe line & accommodate FHTC (350 Nos.) for Ramkrishnapur W/S Scheme under JJM within Daspur-II Block of Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000075/2024-2025 | 2788/MD | 03/09/2024 | 17/11/2024 | GOBINDA MAITY | 44.45 | 0 | 0 | 0
Total | [13 empty] | 1671.46 | 271.08 | 16.22