## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. | SM/11624 | New | Construction of M.S. Fabricated and R.C.C Supporting Structure including aligning pipe line in connection of laying distribution main of Jote Kanuramgarh & Ranichak Water supply scheme under Midnapore Division P.H.E. Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000628/2022-2023 | 453/MD | 13/02/2023 | 14/04/2023 | GOBINDA MAITY | 50.85 | 0 | 0 | 60
2 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. | SM/11624 | New | Construction of Approach Road, Land development (workable to running const. work) at Head Works of Ranichak Water Supply Scheme, Block: - Daspur- I, District: - Paschim Medinipur under Midnapore Division P.H.E. Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000101/2023-2024 | 2476/MD | 14/07/2023 | 04/08/2023 | GOBINDA MAITY | 8.23 | 7.99 | 97.03 | 100
3 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. | SM/11624 | New | Material Requisition To Resource Division |  |  | RTOR000165/2022-2023 | 881/MD | 29/03/2023 | 29/03/2023 | Resource Division | 37.57 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. | SM/11624 | New | Material Requisition To Resource Division |  |  | RTOR000168/2022-2023 | 903/MD | 31/03/2023 | 31/03/2023 | Resource Division | 37.56 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. | SM/11624 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. |  |  | BILL/00720/2022-2023 | 22-23-707,8,9 | 13/03/2023 | 13/03/2023 | GOBINDA MAITY | 61 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. | SM/11624 | New | Electric quotaion for tw-I of Ranichak w/s scheme(consumar ID-203974580) |  |  | BILL/00097/2023-2024 | BP-2023-24-20 | 28/04/2023 | 28/04/2023 | WBSEDCL | 3 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. | SM/11624 | New | Electric quotation for tw-II of Ranichak w/s scheme(consumar ID-203974585) |  |  | BILL/00099/2023-2024 | BP-2023-24-19 | 28/04/2023 | 28/04/2023 | WBSEDCL | 2.15 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. | SM/11624 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001310/2022-2023 | 2312/W/MMD | 29/12/2022 | 27/06/2023 | ECO ENTERPRISE | 25.26 | 25.11 | 99.4 | 100
9 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. | SM/11624 | New | Material Requisition To Resource Division |  |  | RTOR000027/2024-2025 | 3346/MD | 25/11/2024 | 25/11/2024 | Resource Division | 17 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. | SM/11624 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000499/2022-2023 | 2364/MD | 21/11/2022 | 16/04/2026 | GOBINDA MAITY | 1460.37 | 314.91 | 21.56 | 58
11 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. | SM/11624 | New | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001562/2023-2024 | 1211/MMSD-I | 29/09/2023 | 30/12/2023 | SUBHASIS ROY | 0.45 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. | SM/11624 | New | Laying additional distribution system pipe line & accommodate FHTC (650 Nos.) for Ranichak W/S Scheme under JJM within Daspur-II Block of Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000076/2024-2025 | 2789/MD | 03/09/2024 | 01/11/2025 | GOBINDA MAITY | 60.71 | 0 | 0 | 30
13 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. | SM/11624 | New | Laying of Rising main including interconnection of Ranichak & its adjoining mouzas W/S Scheme under Daspur-II block within Ghatal Sub-Division of Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000416/2024-2025 | 197/MD | 17/01/2025 | 16/02/2025 | PALASH KUMAR DAS | 6.38 | 0 | 0 | 100
Total | [13 empty] | 1770.54 | 348 | 19.66