## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/11811 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Debhog PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/000431/2021-2022 | 1664/MD | 28/09/2021 | 08/10/2021 | SIRCON ENGINEERING SERVICES PVT. LTD. | 2.19 | 2.15 | 98.13 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/11811 | Augmentation | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to accommodate FHTC under JJM of Sabang Block in Paschim Medinipur District under Medinipur Division, PHE Dte. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000476/2022-2023 | 2271/MD | 09/11/2022 | 24/12/2022 | S.T. ENTERPRISE | 46.36 | 42.27 | 91.19 | 77
3 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/11811 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001303/2022-2023 | 2305/W/MMD | 29/12/2022 | 27/06/2023 | SUBHASIS ROY | 10.78 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/11811 | Augmentation | Providing and installation of submersible pumping machineries and other electromechanical equipment at newly sunk tube well at Additional TW IV of Debhog water supply scheme under Midnapore Mechanical Division, P.H.E. DTE. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division | ORD/001482/2022-2023 | 1333/MMSD-I | 26/12/2022 | 10/01/2023 | DEBJYOTI BASU | 4.37 | 3.76 | 86.12 | 50
5 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/11811 | Augmentation | Providing and installation of submersible pumping machineries and other electromechanical equipment at newly sunk tube well at Additional TW III of Debhog water supply scheme under Midnapore Mechanical Division, P.H.E. DTE. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division | ORD/001446/2022-2023 | 1334/MMSD-I | 26/12/2022 | 10/01/2023 | DEBJYOTI BASU | 4.37 | 3.68 | 84.29 | 50
6 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/11811 | Augmentation | Supply and delivery at site Submersible pumping machinery and other electro-mechanical equipment in connection with Rejuvenation of Ground water based piped piped water supply scheme for PH No IV of Debhog Part to accommodate FHTC under Sabang Block in Paschim Medinipur District under M.M.D,.PH.E. DTE. TSM009949 |  |  | ORD/000235/2023-2024 | 601/MMSD-I | 05/06/2023 | 20/06/2023 | SUBHASIS ROY | 5.76 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/11811 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002243/2022-2023 | 186/MMSD-I | 27/02/2023 | 30/08/2023 | M/S BIKASH DE | 0.9 | 0.06 | 6.68 | 25
8 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/11811 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002284/2022-2023 | 187/MMSD-I | 27/02/2023 | 30/08/2023 | SUBHASIS ROY | 0.9 | 0.07 | 7.82 | 100
9 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/11811 | Augmentation | Service Connection charges of WBSEDCL for Additional T/W-III of Debhog Water Supply Scheme (Consumer No. 2004156111) |  |  | BILL/00045/2022-2023 | BP-2022-23-88 | 04/01/2023 | 04/01/2023 | WBSEDCL | 2.2 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/11811 | Augmentation | Service Connection charges of WBSEDCL for Additional T/W-IV of Debhog Water Supply Scheme (Consumer No. 2004156795) |  |  | BILL/00044/2022-2023 | Bp-2022-23-87 | 10/01/2023 | 10/01/2023 | WBSEDCL | 0.19 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/11811 | Augmentation | SUPPLY AND DELIVERY OF FUEL FOR INSPECTION VEHICAL FOR INSPECTION OF JJM WORK AT OFFICE OF THE ASSISTANT ENGINEER MMSD1 | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002279/2022-2023 | 186./MMSD-I | 27/02/2023 | 30/08/2023 | M/S BIKASH DE | 3 | 0.2 | 6.82 | 100
Total | [13 empty] | 81.01 | 52.2 | 64.44