## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Bhagirathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/11858 | New | Preparation of D.P.Rs (Consultancy work) in connection with the Proposed Mini Pipe Water Supply Scheme for Mouza- (i) Jamira & (ii) Bhagirathpur under Dewanchak-II Gram Panchayat of SAGY (Sanshad Adarshya Gram Yagona) within Ghatal Block under Midnapore Division, P.H.E. Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000414/2021-2022 | 1312/MD | 16/08/2021 | 26/08/2021 | SIRCON ENGINEERING SERVICES | 3.75 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Bhagirathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/11858 | New | Service connection charge of WBSEDCL at Bhagirathpur Zone-I |  |  | BILL/00038/2022-2023 | BP-2022-23-96 | 11/01/2023 | 11/01/2023 | WBSEDCL | 0.13 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Bhagirathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/11858 | New | Service Connection charges of WBSEDCL at Bhagirathpur TW -II Water Supply Scheme Chowka |  |  | BILL/00040/2022-2023 | BP-2022-23-97 | 11/01/2023 | 11/01/2023 | WBSEDCL | 0.13 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Bhagirathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/11858 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Bhagirathpur (Zone-I), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000222/2022-2023 | 1729/MD | 23/08/2022 | 20/01/2023 | PULLOCK KUMAR GHOSH | 43.24 | 0 | 0 | 75
5 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Bhagirathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/11858 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Bhagirathpur (Zone-II), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000223/2022-2023 | 1730/MD | 23/08/2022 | 20/01/2023 | PULLOCK KUMAR GHOSH | 50.14 | 0 | 0 | 70
6 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Bhagirathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/11858 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Mini Piped Water Supply Scheme for Bhagirathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001315/2022-2023 | 2317/W/MMD | 29/12/2022 | 27/06/2023 | M/S EMMESS | 6.01 | 0 | 0 | 90
7 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Bhagirathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/11858 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Mini Piped Water Supply Scheme for Bhagirathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. (Zone-II) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001973/2022-2023 | 883/W/MMD | 27/03/2023 | 23/09/2023 | RISHAV ENTERPRISE | 6 | 0 | 0 | 100
8 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Bhagirathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. | SM/11858 | New | Material Requisition To Resource Division |  |  | RTOR000041/2024-2025 | 3350/MD | 25/11/2024 | 25/11/2024 | Resource Division | 2.87 | 0 | 0 | 0
Total | [13 empty] | 112.26 | 0 | 0