## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Kelegoda & its adjoining mouzas. | SM/11879 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Kelegoda & its adjoining Mouzas PWSS Block - Ghatal under Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000928/2021-2022 | 529/MD | 21/03/2022 | 10/04/2022 | GOBINDA MAITY | 4.86 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Kelegoda & its adjoining mouzas. | SM/11879 | New | Material Requisition To Resource Division |  |  | RTOR000005/2023-2024 | 944/MD | 05/04/2023 | 05/04/2023 | Resource Division | 26.63 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kelegoda & its adjoining mouzas. | SM/11879 | New | Electric quotation bill for Tw no-I of Kelegoda water supply scheme. Ref Consumer ID-204087644. |  |  | BILL/02665/2023-2024 | BP-2023-24-264 | 26/09/2023 | 26/09/2023 | WBSEDCL | 3.99 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kelegoda & its adjoining mouzas. | SM/11879 | New | Electric Quotation bill for Tw No-II of Kelegoda water supply scheme. Ref Consumer ID-204087648. |  |  | BILL/02666/2023-2024 | BP-2023-24-263 | 26/09/2023 | 26/09/2023 | WBSEDCL | 2.87 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Kelegoda & its adjoining mouzas. | SM/11879 | New | Material Requisition To Resource Division |  |  | RTOR000024/2024-2025 | 3343/MD | 25/11/2024 | 25/11/2024 | Resource Division | 10.47 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Kelegoda & its adjoining mouzas. | SM/11879 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 2 nos. 400 cum OHR (Intze type with pile foundation) & 3 Nos. 300 Cum OHR & Accommodate FHTC (10,944 Nos,) under JJM with allied work for (i) Chaipat (Zone-I & Zone-II) & its adjoining mouzas W/S scheme (ii) Kelegoda & its adjoining mouzas W/S Scheme (iii) Uttarbar (Zone-I & Zone-II) & its adjoining mouzas W/S Scheme in Daspur- II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000514/2022-2023 | 2556/MD | 15/12/2022 | 05/02/2026 | M/S. S.S. ENTERPRISE | 2473.34 | 0 | 0 | 18
7 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kelegoda & its adjoining mouzas. | SM/11879 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based PWSS for Kelegoda & its adjoining mouzas Dist-Paschim Medinipur under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001300/2022-2023 | 2302/W/MMD | 29/12/2022 | 18/12/2024 | DEBJYOTI BASU | 22.87 | 0 | 0 | 50
Total | [13 empty] | 2545.04 | 0 | 0