## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/11898 | Augmentation | Conducting of Route Survey in connection with the Functional Household Tap Connection of existing PWSS (Belda, Block - Narayangarh) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000119/2021-2022 | 1008/MD | 24/06/2021 | 04/07/2021 | SIRCON ENGINEERING SERVICES | 4.22 | 0 | 0 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/11898 | Augmentation | Design with allied works in connection with the Functional Household Tap Connection of existing PWSS (Belda, Block ¿ Narayangarh) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000153/2021-2022 | 965/MD | 18/06/2021 | 28/06/2021 | SIRCON ENGINEERING SERVICES | 3.9 | 0 | 0 | 100
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/11898 | Augmentation | Preparation of DPR with allied works in connection with the Functional Household Tap Connection of existing PWSS (Belda, Block - Narayangarh) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000120/2021-2022 | 1009/MD | 24/06/2021 | 04/07/2021 | SIRCON ENGINEERING SERVICES | 1.19 | 0 | 0 | 100
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/11898 | Augmentation | Repairing of Damage pipe line (AC) at Mouza Deuli, Kusmuri, Sarisha of Belda Zone II W/S Scheme within Narayangarh Block under Kharagpur Sub-Division under Midnapore Division P.H.E. Dte. | AE/RWS Midnapore Sub Division |  | ORD/000397/2021-2022 | 496/AE/KSD | 30/11/2021 | 30/12/2021 | NIMAI LAL GURIA | 0.52 | 0 | 0 | 100
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/11898 | Augmentation | Sinking of (Two) nos. 300 X 200 mm dia. X 200mtr. depth deep tube well by direct rotary method for Augmentation of Belda PWSS (Zone-I & II) with in Narayangarh Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | ORD/000664/2022-2023 | 583/MD | 23/02/2023 | 09/03/2023 | M/S. A.R. ENTERPRISE. | 23.69 | 0 | 0 | 80
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/11898 | Augmentation | Continuation Work Order for the work of Conducting of Route Survey in connection with the Functional Household Tap Connection of existing PWSS (Belda, Block - Narayangarh) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/001090/2021-2022 | 1108/MD | 09/07/2021 | 19/07/2021 | SIRCON ENGINEERING SERVICES | 3.74 | 0 | 0 | 100
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/11898 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000025/2022-2023 | 132/MD | 11/01/2023 | 11/01/2023 | Resource Division | 38.43 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/11898 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000170/2023-2024 | 1364/MD | 02/05/2023 | 02/05/2023 | Resource Division | 49.19 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/11898 | Augmentation | Laying distribution pipe line, Providing FHTC (2,538 Nos.), Soil test and Construction of R.C.C. Over Head Reservoir of capacity 250 Cum and staging height 20.00 mtr. with allied work under Augmentation of Belda Zone-I & its adjoining mouzas Water Supply Scheme within Narayangarh Dev. Block including supply of all labour & materials under Midnapore Division, P.H.E. Dte. Dist. Paschim Medinipur. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE1 Kharagpur Sub-division,JE2 Kharagpur Sub Division | ORD/000009/2023-2024 | 1020/MD | 12/04/2023 | 05/04/2025 | DULAL CHANDRA DAS | 561.63 | 0 | 0 | 20
10 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/11898 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division | ORD/001608/2022-2023 | 531/W/MMD | 20/03/2023 | 16/09/2023 | BHABANI PRASAD MANNA | 22.79 | 0 | 0 | 80
11 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/11898 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000130/2024-2025 | 3466/MD | 25/11/2024 | 25/11/2024 | Resource Division | 1.63 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/11898 | Augmentation | Laying distribution pipe line, Soil test and Construction of R.C.C. Over Head Reservoir of capacity 200 Cum and staging height 20.00 mtr. with allied work under Augmentation of Belda Zone-II & its adjoining moujas Water Supply Scheme within Narayangarh Dev. Block including supply of all labour & materials under Midnapore Division, P.H.E. Dte. Dist. Paschim Medinipur. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE1 Kharagpur Sub-division,JE2 Kharagpur Sub Division | ORD/000470/2022-2023 | 2188/MD | 01/11/2022 | 30/04/2023 | BANERJEE CONSTRUCTION | 558.93 | 0 | 0 | 50
13 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/11898 | Augmentation | Continuation Work order For "Casual hiring of Inspection vehicle for Jal Jeevan Mission on an ¿as and when required¿ basis, Motor cab (Standard) commercial with catalytic converter attachment with Bharat Stage as per prevalent applicable standard compliant new/not older than 30 (Thirty) months from the date of 1st Registration on daily hire basis for the tenure of (01.08.2024 to 31.01.2025) only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use under Midnapore Division, PHE Dte." | Assistant Engineer (HQ) |  | ORD/000062/2024-2025 | 2338/MD | 30/07/2024 | 29/01/2025 | PULLOCK KUMAR GHOSH | 0.87 | 0 | 0 | 0
14 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/11898 | Augmentation | Construction of Boundary wall at Head work site for Augmentation of Belda (Zone-I) W/S Scheme within Narayangarh Block under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE2 Kharagpur Sub Division | ORD/000382/2024-2025 | 57/MD | 07/01/2025 | 02/01/2026 | K & KABERI ENTERPRISE (PROP. GOUTAM MAITY) | 13.65 | 0 | 0 | 75
15 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/11898 | Augmentation | Continuation Work order For "Casual hiring of Inspection vehicle for Jal Jeevan Mission as and when required basis Motor cab (Standard) commercial with catalytic converter attachment with Bharat Stage as per prevalent applicable standard compliant new/not older than 30 (Thirty) months from the date of 1st Registration on daily hire basis for the tenure from 01.02.2025 to 31.07.2025 only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use under Midnapore Division, PHE Dte." | Assistant Engineer (HQ) | Junior Engineer_ Estimate Section | ORD/000548/2024-2025 | 308/MD | 28/01/2025 | 27/07/2025 | PULLOCK KUMAR GHOSH | 0.86 | 0 | 0 | 0
Total | [13 empty] | 1285.21 | 0 | 0