## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur | SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. (Bashuli) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000156/2022-2023 | 515/AE/GSD | 07/09/2022 | 27/09/2022 | PRITI ENTERPRISE | 4.33 | 4.2 | 96.91 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur | SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte.(Srinagar) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000162/2022-2023 | 521/AE/GSD | 07/09/2022 | 27/09/2022 | A.R. CONSTRUCTION | 4.33 | 4.31 | 99.37 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur | SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte.( Srinagar Madhya para) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000163/2022-2023 | 522/AE/GSD | 07/09/2022 | 27/09/2022 | PULLOCK KUMAR GHOSH | 4.33 | 0.18 | 4.22 | 100
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur | SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. ( Kochgeria) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000157/2022-2023 | 516/AE/GSD | 07/09/2022 | 27/09/2022 | PULLOCK KUMAR GHOSH | 4.33 | 4.1 | 94.55 | 100
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur | SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. (Rejna) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000159/2022-2023 | 518/AE/GSD | 07/09/2022 | 27/09/2022 | INDRAJIT ROY | 4.33 | 4.15 | 95.73 | 100
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur | SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. (Jara Uttar Para) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000154/2022-2023 | 513/AE/GSD | 07/09/2022 | 27/09/2022 | TARUN MAHATA | 4.33 | 4.32 | 99.75 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur | SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte.(Narayanpur) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000158/2022-2023 | 517/AE/GSD | 07/09/2022 | 27/09/2022 | BUNBA CONSTRUCTION | 4.33 | 4.33 | 99.93 | 100
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur | SM/12117 | Retrofitting | Retrofitting to accomodate FHTC under JJM ar Srinagar water supply scheme Block-Candrakona-I and II District Paschim Medinipur within Midnapore Division P.H.E.Dte. (Rejna) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000058/2023-2024 | 336/AE/GSD | 16/05/2023 | 05/06/2023 | INDRAJIT ROY | 1.45 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur | SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte.( Maide) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000165/2022-2023 | 524/AE/GSD | 07/09/2022 | 27/09/2022 | M/S. ZAMAN ENTERPRISE | 3.31 | 3.15 | 94.96 | 0
10 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur | SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. (Jara Purba Para.) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000152/2022-2023 | 511/AE/GSD | 07/09/2022 | 27/09/2022 | M/S JITEN BANARJEE | 4.33 | 4.25 | 98.16 | 100
11 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur | SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. (Jara Paschim Para) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000153/2022-2023 | 512/AE/GSD | 07/09/2022 | 27/09/2022 | M/S JITEN BANARJEE | 4.33 | 4.27 | 98.54 | 20
12 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur | SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte.(Jara Dakshin Para) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000155/2022-2023 | 514/AE/GSD | 07/09/2022 | 27/09/2022 | KAMAKHYA ENTERPRISE | 4.33 | 4.16 | 95.88 | 100
13 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur | SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. ( Sanpur) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000160/2022-2023 | 519/AE/GSD | 07/09/2022 | 27/09/2022 | SURAJIT GHOSH | 4.33 | 4.27 | 98.54 | 100
14 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur | SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. (Srinagar Purba Para) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000161/2022-2023 | 520/AE/GSD | 07/09/2022 | 27/09/2022 | MAHAPRABHU ENTERPRISE | 4.33 | 4.33 | 99.93 | 100
15 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur | SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte.( Mahabala) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000164/2022-2023 | 523/AE/GSD | 07/09/2022 | 27/09/2022 | M/S. ZAMAN ENTERPRISE | 4.33 | 4.33 | 99.81 | 100
16 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur | SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. (Rejna) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000059/2023-2024 | 337/AE/GSD | 16/05/2023 | 05/06/2023 | INDRAJIT ROY | 1.45 | 1.26 | 86.86 | 100
17 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur | SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. ( Kochgeri |  |  | BILL/00670/2023-2024 | BP-2022-23-608 | 01/09/2023 | 01/09/2023 | PULLOCK KUMAR GHOSH | 4.25 | 0 | 0 | 0
18 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur | SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. ( Kochgeria) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/001075/2022-2023 | 107/AE.GSD | 13/02/2023 | 05/03/2023 | PULLOCK KUMAR GHOSH | 0.85 | 0.85 | 100 | 100
19 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur | SM/12117 | Retrofitting | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte.( Srinagar Madhya para) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/001076/2022-2023 | 109/AE/GSD | 13/02/2023 | 05/03/2023 | PULLOCK KUMAR GHOSH | 0.4 | 0.4 | 100 | 100
20 | PASCHIM MEDINIPUR |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (PHESE-III), Block - Chandrakona-I & II, District - Paschim Medinipur | SM/12117 | Retrofitting | Laying additional pipelines regarding Balance work of Retrofitting to accommodate FHTC under JJM at SRINAGAR water supply scheme Block-Chandrakona-I & 2 District- Paschim Medinipur within Midnapore Division, PHE.Dte. (Muide, Jara Purba & Mahabala) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000128/2024-2025 | 1494/AE/GSD | 24/09/2024 | 09/10/2024 | M/S JITEN BANARJEE | 3.48 | 0 | 0 | 100
Total | [13 empty] | 71.54 | 56.86 | 79.48