## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Division | ASHARI AND IT'S ADJOINING MOUJAS PWSS | SM/12198 | New | Material Requisition To Resource Division |  |  | RTOR000281/2023-2024 | 4053/MD | 12/10/2023 | 12/10/2023 | Resource Division | 20.09 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | ASHARI AND IT'S ADJOINING MOUJAS PWSS | SM/12198 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for ASHARI AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001899/2022-2023 | 798/W/MMD | 24/03/2023 | 31/12/2025 | BHABANI PRASAD MANNA | 21.62 | 0 | 0 | 80
3 | PASCHIM MEDINIPUR | Debra | Midnapore Division | ASHARI AND IT'S ADJOINING MOUJAS PWSS | SM/12198 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | ORD/000205/2023-2024 | 2821/MD | 07/08/2023 | 01/10/2026 | GOBINDA MAITY | 4353.07 | 153.69 | 3.53 | 25
4 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | ASHARI AND IT'S ADJOINING MOUJAS PWSS | SM/12198 | New | Electrict quotation bill for TW-II of Ashari pwss (Ref Consumar ID-204503747),Application No-2005054112,Application Type-New Connection,Name of CCC-Balichak ccc, block-Debra |  |  | BILL/04216/2024-2025 | C032554729434 | 17/03/2025 | 17/03/2025 | WBSEDCL | 4.33 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | ASHARI AND IT'S ADJOINING MOUJAS PWSS | SM/12198 | New | Electrict quotation bill for TW-I of Ashari pwss (Ref Consumar ID-204503746),Application No-2005054095,Application Type-New Connection,Name of CCC-Balichak ccc, block-Debra |  |  | BILL/04215/2024-2025 | C032554726156 | 17/03/2025 | 17/03/2025 | WBSEDCL | 3.92 | 0 | 0 | 0
Total | [13 empty] | 4403.03 | 153.69 | 3.49