## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | BAKALSABAKARAM PWSS | SM/12199 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BAKALSABAKARAM PWSS Dist-Paschim Medinipur under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001298/2022-2023 | 2301/W/MMD | 29/12/2022 | 27/08/2025 | ECO ENTERPRISE | 23.01 | 14.89 | 64.72 | 50
2 | PASCHIM MEDINIPUR | Debra | Midnapore Division | BAKALSABAKARAM PWSS | SM/12199 | New | Construction of 200 Cum & 300 Cum Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works with laying rising main, distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (4,806 Nos.) including 2 years operation & maintenance For Bakalsabakram, Bhagabanpur and Chak Prayag Pipe water supply Scheme within Debra Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra) | ORD/000470/2023-2024 | 5382/MD | 04/12/2023 | 30/06/2025 | M/S. KAMAK ENGINEERS AND CO. | 1277.59 | 96.46 | 7.55 | 50
3 | PASCHIM MEDINIPUR | Debra | Midnapore Division | BAKALSABAKARAM PWSS | SM/12199 | New | Material Requisition To Resource Division |  |  | RTOR000201/2023-2024 | 1411 | 04/05/2023 | 04/05/2023 | Resource Division | 35.33 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | BAKALSABAKARAM PWSS | SM/12199 | New | Electrict quotation bill for TW-I of Bakalsa Sebakram pwss (Ref Consumar ID-204462534),Application No-2004990841,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra |  |  | BILL/03366/2024-2025 | C122421487248 | 16/12/2024 | 16/12/2024 | WBSEDCL | 8.79 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | BAKALSABAKARAM PWSS | SM/12199 | New | Electrict quotation bill for TW-II of Bakalsa Sebakram pwss (Ref Consumar ID-204511284),Application No-2005065096,Application Type-New Connection,Name of CCC-Lowada ccc, block-Debra |  |  | BILL/04252/2024-2025 | C032554603387 | 27/03/2025 | 27/03/2025 | WBSEDCL | 7 | 0 | 0 | 0
Total | [13 empty] | 1351.72 | 111.35 | 8.24