## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Division | BHAGABANPUR PIPED WATER SUPPLY SCHEME | SM/12202 | New | Material Requisition To Resource Division |  |  | RTOR000202/2023-2024 | 1412 | 04/05/2023 | 04/05/2023 | Resource Division | 24.76 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | BHAGABANPUR PIPED WATER SUPPLY SCHEME | SM/12202 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Bhagabanpur PWSS Dist-Paschim Medinipur under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001295/2022-2023 | 2298/W/MMD | 29/12/2022 | 27/12/2025 | SUBHAM ENTERPRISE | 22.79 | 0 | 0 | 40
3 | PASCHIM MEDINIPUR | Debra | Midnapore Division | BHAGABANPUR PIPED WATER SUPPLY SCHEME | SM/12202 | New | Construction of 200 Cum & 300 Cum Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works with laying rising main, distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (4,806 Nos.) including 2 years operation & maintenance For Bakalsabakram, Bhagabanpur and Chak Prayag Pipe water supply Scheme within Debra Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra) | ORD/000470/2023-2024 | 5382/MD | 04/12/2023 | 30/06/2025 | M/S. KAMAK ENGINEERS AND CO. | 1277.59 | 0 | 0 | 50
Total | [13 empty] | 1325.15 | 0 | 0