## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Division | BIKRAMPUR PWSS | SM/12203 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division |  | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 30/01/2023 | JADAVPUR UNIVERSITY | 100.36 | 4.78 | 4.76 | 90
2 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | BIKRAMPUR PWSS | SM/12203 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BIKRAMPUR PWSS Dist-Paschim Medinipur under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001297/2022-2023 | 2300/W/MMD | 29/12/2022 | 31/10/2025 | P.K.ENGINEERING | 22.8 | 21.11 | 92.58 | 50
3 | PASCHIM MEDINIPUR | Debra | Midnapore Division | BIKRAMPUR PWSS | SM/12203 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works with laying rising main, distribution system , Sinking of Tube Well , Pump House , Boundary Wall, & Providing Functional Household Tap Connection (1430 Nos) including 1 years operation & maintenance For Bikrampur Pipe water supply Scheme within Debra Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | ORD/000204/2023-2024 | 2820/MD | 07/08/2023 | 28/01/2025 | GOBINDA MAITY | 416.11 | 230.86 | 55.48 | 55
4 | PASCHIM MEDINIPUR | Debra | Midnapore Division | BIKRAMPUR PWSS | SM/12203 | New | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 1144/MD | 25/04/2023 | 25/04/2023 | Resource Division | 16.01 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | BIKRAMPUR PWSS | SM/12203 | New | Electrict quotation bill for TW-II of BIKRAMPUR pwss (Ref Consumar ID-204198610),Application No-2004571249,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra. |  |  | BILL/03569/2023-2024 | BP-2023-24-605 | 07/02/2024 | 07/02/2024 | WBSEDCL | 5.54 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | BIKRAMPUR PWSS | SM/12203 | New | Electrict quotation bill for TW-I of Bikrampur pwss (Ref Consumar ID-204197919),Application No-2004569264,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra. |  |  | BILL/03556/2023-2024 | BP-2023-24-611 | 07/02/2024 | 07/02/2024 | WBSEDCL | 4.1 | 0 | 0 | 0
Total | [13 empty] | 564.91 | 256.74 | 45.45