## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | KASHBAASANDA AND ADJOINING MOUJAS PWSS at Narayangrah under Midnapore Division P.H.E.Dte. | SM/12331 | New | Material Requisition To Resource Division |  |  | RTOR000026/2023-2024 | 1175/MD | 26/04/2023 | 26/04/2023 | Resource Division | 28.44 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | KASHBAASANDA AND ADJOINING MOUJAS PWSS at Narayangrah under Midnapore Division P.H.E.Dte. | SM/12331 | New | Quotation for new power connection at Kasba Asanda PWSS T/W - I Within Narayangarh Block Application No - 2004987922, Ref ID- 204460782 |  |  | BILL/03871/2024-2025 |  | 24/12/2024 | 24/12/2024 | WBSEDCL | 3.7 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | KASHBAASANDA AND ADJOINING MOUJAS PWSS at Narayangrah under Midnapore Division P.H.E.Dte. | SM/12331 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection 14,471 Nos.) including 2 years operation & maintenance for Radhanagar, Akanda, Kashbaasanda, Kutki, Tarua, Trikalpur, Uttar Karkara and Shashinda Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE2 Kharagpur Sub Division | ORD/000212/2023-2024 | 2823/MD | 07/08/2023 | 24/03/2026 | S & P ENTERPRISE | 3925.58 | 0 | 0 | 20
4 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | KASHBAASANDA AND ADJOINING MOUJAS PWSS at Narayangrah under Midnapore Division P.H.E.Dte. | SM/12331 | New | Improvement of approach road of Kasbasanda PWSS Head work site under Narayangarh block within Midnapore Division, PHE Dte. [Length 60.0 Mtr. X Width 2.0 Mtr. (av.) X Depth 1.50 Mtr. (av.)] | Assistant Engineer (HQ) |  | ORD/000005/2025-2026 | 996/AE/HQ/MD | 22/04/2025 | 22/05/2025 | GOURMOHAN DAS | 2.31 | 0 | 0 | 0
Total | [13 empty] | 3960.03 | 0 | 0