## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-I | Midnapore Division | KUILABAD AND ADJOINING MOUJAS PWSS at Garbeta-I Block. | SM/12335 | New | Material Requisition To Resource Division |  |  | RTOR000160/2022-2023 | 1156/MD | 25/04/2023 | 25/04/2023 | Resource Division | 33.76 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Garbeta-I | Jhargram Mechanical Division | KUILABAD AND ADJOINING MOUJAS PWSS at Garbeta-I Block. | SM/12335 | New | new service connection charges at Kuilabad T/W-II |  |  | BILL/01415/2024-2025 | 426/JMD | 28/11/2024 | 28/11/2024 | WBSEDCL | 5.59 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Garbeta-I | Jhargram Mechanical Division | KUILABAD AND ADJOINING MOUJAS PWSS at Garbeta-I Block. | SM/12335 | New | new service connection charges at Kuilabad TW-I water supply scheme |  |  | BILL/00976/2024-2025 | 338/JMD | 05/09/2024 | 05/09/2024 | WBSEDCL | 12.35 | 0 | 0 | 0
Total | [13 empty] | 51.7 | 0 | 0