## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | BRINDABANPUR AND ITS ADJOINING MOJAS PWSS | SM/12384 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BRINDABANPUR AND ITS ADJOINING MOJAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000009/2023-2024 | 1125/W/MMD | 12/04/2023 | 09/10/2023 | S.P. ENTERPRISE | 22.65 | 8.21 | 36.23 | 50
2 | PASCHIM MEDINIPUR | Debra | Midnapore Division | BRINDABANPUR AND ITS ADJOINING MOJAS PWSS | SM/12384 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | ORD/000205/2023-2024 | 2821/MD | 07/08/2023 | 01/10/2026 | GOBINDA MAITY | 4353.07 | 254.4 | 5.84 | 45
3 | PASCHIM MEDINIPUR | Debra | Midnapore Division | BRINDABANPUR AND ITS ADJOINING MOJAS PWSS | SM/12384 | New | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 1196 | 26/04/2023 | 26/04/2023 | Resource Division | 31.5 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | BRINDABANPUR AND ITS ADJOINING MOJAS PWSS | SM/12384 | New | Electrict quotation bill for TW-I of Brindabanpur pwss (Ref Consumar ID-204468497),Application No-2005000146,Application Type-New Connection,Name of CCC-Lowada ccc, block-Debra |  |  | BILL/03641/2024-2025 | C012524050658 | 09/01/2025 | 09/01/2025 | WBSEDCL | 3.55 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | BRINDABANPUR AND ITS ADJOINING MOJAS PWSS | SM/12384 | New | Electrict quotation bill for TW-II of Bindabanpur pwss (Ref Consumar ID-204631841),Application No-2005237496,Application Type-New Connection,Name of CCC-Lowada ccc, block-Debra |  |  | BILL/00900/2025-2026 | 42156 | 07/08/2025 | 07/08/2025 | WBSEDCL | 7.97 | 0 | 0 | 0
Total | [13 empty] | 4418.75 | 262.61 | 5.94