## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Division | CHAK SULPAN AND IT'S ADJOINING MOUJAS PWSS | SM/12412 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division |  | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 30/01/2023 | JADAVPUR UNIVERSITY | 100.36 | 4.78 | 4.76 | 90
2 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | CHAK SULPAN AND IT'S ADJOINING MOUJAS PWSS | SM/12412 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for CHAK SULPAN AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001948/2022-2023 | 828/W/MMD | 24/03/2023 | 20/09/2023 | ORIENTAL ENGINEERING CO. | 22.65 | 10.53 | 46.49 | 50
3 | PASCHIM MEDINIPUR | Debra | Midnapore Division | CHAK SULPAN AND IT'S ADJOINING MOUJAS PWSS | SM/12412 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works with laying rising main, distribution system , Sinking of Tube Well , Pump House , Boundary Wall, & Providing Functional Household Tap Connection (6348 Nos) including 2 years operation & maintenance For Chak Sulpan, Katai, Khanamohan, Khamra and Kumarsanda Pipe water supply Scheme within Debra Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE1 Kharagpur Sub-division | ORD/000064/2023-2024 | 2145/MD | 08/06/2023 | 29/04/2026 | GOBINDA MAITY | 1960.6 | 122.23 | 6.23 | 65
4 | PASCHIM MEDINIPUR | Debra | Midnapore Division | CHAK SULPAN AND IT'S ADJOINING MOUJAS PWSS | SM/12412 | New | Material Requisition To Resource Division |  |  | RTOR000008/2023-2024 | 1149/MD | 25/04/2023 | 25/04/2023 | Resource Division | 16.14 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | CHAK SULPAN AND IT'S ADJOINING MOUJAS PWSS | SM/12412 | New | Electrict quotation bill for Chaksulpan water supply scheme pump house NO-I(Consumar Id-204134472) |  |  | BILL/02962/2023-2024 | BP-2023-24-362 | 24/11/2023 | 24/11/2023 | WBSEDCL | 4.7 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | CHAK SULPAN AND IT'S ADJOINING MOUJAS PWSS | SM/12412 | New | Electrict quotation bill for TW-II of Chaksulpan pwss (Ref Consumar ID-204458742),Application No-2004983505,Application Type-New Connection,Name of CCC-Balichak ccc, block-Debra |  |  | BILL/03656/2024-2025 | C012524054025 | 09/01/2025 | 09/01/2025 | WBSEDCL | 7.5 | 0 | 0 | 0
Total | [13 empty] | 2111.94 | 137.54 | 6.51